## 1. Board Ventilation Strategy
The column titles for this worksheet are in rows 3, 7, 8, and 11. They span cells A3, A7, A8 through B8, and A11. The data spans cells A9 through B9, and A12 through A15. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
School boards are optimizing air quality in schools through improved ventilation and filtration. Implemented measures are dependent on the type of ventilation and feasibility within the context of school facilities and related building systems.
Ventilation
Filtration
School Board Ventilation Profile
Measures to optimize ventilation in schools
Ventilation: Increasing the flow of outdoor/fresh air for diluting the concentration of any infectious particles.
Filtration: Involves the use of different types of fibrous media designed to remove particles from the airstream.
SCHOOL Board Ventilation Strategy

## 2. Board Level Investments
The column titles for this worksheet are in rows 5, 6, 7, and 12. They span cells A5, A6, A7 through B7, and A12. The data spans cells A8 through B11, and A12 through B12. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
School Board Ventilation Profile
Durham District School Board
Ventilation Funding* |
$45.9M
54
Ventilation projects completed
SCHOOL BOARD wide investments
Ventilation projects in progress / planned
11
2020-21 - 2024-25
Note: *This includes spending from dedicated ventilation programs, federal-provincial funding, provincial renewal funding and supplemental funding from other board sources.
132
Schools receiving an investment, which is of total schools in the board.
Schools to receive an investment, which is
of total schools in the board.
132
sTANDALONE HEPA FILTER UNITs dEPLOYED |
2251
97%
97%
Planned Ventilation Projects |
$15.4M
2025-2026

## 3. School Dashboard
The column titles for this worksheet are in rows 5, 7, and 9. They span cells A5, A7, and A9. The data spans cells B10 through F19. Cell D5 has Sort options. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
| School Name | Adelaide Mclaughlin P.S.
| Ventilation System | Mechanical Ventilation
School Ventilation and Filtration Measures*
| Ventilation assessed |  | 1 | Yes
| Higher grade filters installed |  | 1 | Yes
| Increased frequency of filter changes |  | 1 | Yes
| Increased fresh air intake (windows and/or mechanical ventilation systems) |  | 1 | Yes
| Standalone HEPA** filter units deployed in portables, as needed |  | 1 | Yes
| Standalone HEPA filter units in place |  | 21
*Some measures may not be feasible within the context of a school facility/site and related building systems.
**High-Efficiency Particulate Air (HEPA)
School Board Ventilation Profile
Select your school here

## 4. Board Level Worksheet (hidden)
The column titles for this worksheet are in rows 1, 3, 13, 15, 16, and 17. They span cells B1 through C1, B3, B13, E15 through P15, E16 through P16, and E17 through P17. The data spans cells A5 though C29, and E18 through P19. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader. | Question | Input Response:
Legend
| TAB 1: Board Ventilation Strategy |  |  |  |  | Calculated field
Data entry field
1 | Select Board Name | Durham District School Board | <- Select
2 | Identify your board strategy (in four bullets)
2.1 |  | ENHANCE PERFORMANCE: Increase the minimum ventilation rate on all HVAC systems, including a full air exchange post and pre occupied times. Recommission all pneumatic controls and existing HVAC systems to maintain optimal performance. | <- Enter here
2.2 |  | INCREASE EQUIPMENT/MATERIALS: Purchase 2200 portable HEPA air filtration units (The Ministry of Education has supplied an additional 386 units). Invest in upgraded filters from MERV 7 to MERV 13 for all ventilation systems. | <- Enter here
2.3 |  | MONITOR & VERIFY: Complete a system ventilation check in every building. Recalibrate systems to optimize air flow within each building. Monitor building automation systems daily for any HVAC related issues. | <- Enter here
2.4 |  | PREVENTATIVE MAINTENANCE: Increase filter change frequency. Utilize duct cleaning services to aid in the efficiency of ventilation systems and to enhance air quality. | <- Enter here
TAB 2: Board Level Investments
[23 empty] | x | x |  |  |  |  | x | x
3 | Investments and Projects |  |  | Funding Sources (Please Complete Expenditure Details)
|  |  |  | 2020-21 | [5 empty] | 2021-22 | [6 empty] | 2022-23 | [5 empty] | 2023-24 | [5 empty] | 2024-25 | [5 empty] | 2025-26
|  | Calculated fields (3.1, 3.2, 3.5 and 3.8) |  | $50M-Ventilation | $50M-Ventilation | ICIP-CVRIS (Spent) | SRA (Spent on Ventilation) | SCI (Spent on Ventilation) | Other Board Funding (Spent on Ventilation) | $29.4M for filters and utilities | HEPA Funding | Hepa Funding (Approx. $ value for HEPA units provided) | SRA (Spent on Ventilation) | SCI (Spent on Ventilation) | ICIP-CVRIS (Spent) | Other Board Funding (Spent on Ventilation) | SRTCF Funding | ICIP-Ventilation Funding | SRA (Spent on Ventilation) | SCI (Spent on Ventilation) | ICIP-CVRIS (Spent) | Other Board Funding (Spent on Ventilation) | SRTCF Funding | ICIP-Ventilation Funding | SRA (Spent on Ventilation) | SCI (Spent on Ventilation) | ICIP-CVRIS (Spent) | Other Board Funding (Spent on Ventilation) | SRTCF Funding | ICIP-Ventilation Funding | SRA (Spent on Ventilation) | SCI (Spent on Ventilation) | ICIP-CVRIS (Spent) | Other Board Funding (Spent on Ventilation) | SRTCF Funding | ICIP-Ventilation Funding | SRA (Spent on Ventilation) | SCI (Spent on Ventilation) | ICIP-CVRIS (Spent) | Other Board Funding (Spent on Ventilation)
3.1 | Ventilation Funding Allocated since 2020-21 | 45.8787 |  | 1.4395 | 1.4395 | 3.31 | 0.46159 | 0.94 | 0.59 | 0.99996 | 0.171 | 0.37486 | 2.4146 | 2.21 | 2.68 | 0.71 | 0.89909 | 0.67121 | 1.7451 | 5.5421 | 0.099667 | 1.2138 | 0 | 0 | 3.878 | 5.3172 | 0 | 1.4415 | 0 | 0 | 2.17 | 5.11 | 0 | 0.05 | 0 | 0 | 2.75 | 12.64 | 0 | 0
3.2 | Planned Ventilation Projects 2025-26 | 15.39
3.3 | Ventilation Projects Completed since 2020-21 (2020-21 to 2024-25) | 54 | <- Enter here
3.4 | Number of Schools that receieved an investment since 2020-21 (2020-21 to 2024-25) | 132 | <- Enter here | only 132/136 - 4 new schools had no CVRIS funded items, no ventilation projects, and no HEPA units deployed (Beaver River, Josiah Henson, Maamawaii, Trilliam Woods)
3.5 | % of Schools Open and Operating Receiving an Investment (2024-25) | 97.06% | <- Calculated
3.6 | Ventilation Projects to be Completed (2025-26) | 11 | <- Enter here
3.7 | Number of Schools planned to receive an Investment (2025-26) | 132 | <- Enter here | only 132/136 - 4 new schools had no CVRIS funded items, no ventilation projects, and no HEPA units deployed (Beaver River, Josiah Henson, Maamawaii, Trilliam Woods)
3.8 | % of Schools Open and Operating Receiving an Investment (2025-26) | 97.06% | <- Calculated
3.9 | Standalone HEPA Filter Units Deployed | 2251 | <- Enter here
** I left Thorah out of 3.4 so we don't create confusion
** Also I deleted Grove because DASS also has an entry already
134 original, remove Thorah and Grove, Add Beaver River and Maamawai
** First report started at 40 projects. 2024-25 added 6 projects.
From Mike:
As discussed, let’s move the 6 from 2024/25 over to the 40 for a total of 46.
For the 2024/25 Projects to be completed, we can use 8 projects as out number without windows. With windows, we have 10.
2024/25
1. Dunbarton HS – Main Campus - Dust collector replacement
2. Dunbarton HS – South Campus – Ventilation upgrade phase 1
3. J.Clarke Richardson CVI – Chiller replacement
4. Scott Central PS – Ventilation upgrade (new)
5. DASS Simcoe – Air conditioning
6. Hillsdale PS – Library, office, & SERT air conditioning
7. R.H. Cornish PS – Gym to classrooms conversion including RTU replacement
8. Brock HS – Dust Collector Replacement
Not sure if we are adding windows, but, if so, the following projects apply:
9. Port Perry HS – Phase 4 – Original building window replacement
10. Ajax HS – 1954, 62, 63 additions window replacements
** Previously reported 46 projects completed, add 8 reported LY = 54
List Confirmed by Mike - 2026-06-08
2025/26
2025 - Ventilation - Dunbarton HS
2026 - Cooling Tower Repairs - Pine Ridge SS
2026 - HVAC Upgrade - Brock HS (**Under Rewview, may cancel/postpone)
2026 - Office Air Conditioning - Ormiston PS
2026 - HVAC & AHU Replacement - Vaughan Willard PS
2026 - HVAC - Ventilation & DHW Replacement - Lincoln Avenue PS
2025 - HVAC A/C Upgrade - Culinary Arts - Eastdale CVI
2026 - Ventilation & Controls Upgrade Ph 2 - Dunbarton HS - South Campus
2026 - Dust Collector Replacement - Ajax HS
2026 - Dust Collector - O'Neill CVI
2026 - Ventilation - Dust Collector - Anderson CVI
Total = 11 projects to be completed 2025/26

## 5. School Level Worksheet (hidden)
The column titles for this worksheet are in rows 2, 4, and 5. They span cells A2 through N2, A4 through N4, and A5 through N5. The data spans cells A6 through O114. Cells A5 through M5 have Sort options. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader.
These are drop down options → |  | Mechanical Ventilation, Partial Mechanical Ventilation, Non-Mechanical Ventilation (Natural Ventilation / Exhaust Only) | Yes/No/NA |  | Yes/No/NA | Yes/No/NA | Yes/No/NA | Yes/No/NA | Numbers #
Enter School Details |  |  | Identify Ventilation Measures
Name of School Facility | Building ID | Type of School Facility Ventilation | Ventilation assessed | Higher grade filters installed | Increased frequency of filter changes | Increased fresh air intake (windows and/or mechanical ventilation systems) | HEPA units deployed in portables, as needed | Standalone HEPA filter units in place | Board ID
Adelaide Mclaughlin P.S. | 5314-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 21 | 13 | =INDEX(Table2[Count of Equipment '#],MATCH([@[Building ID]],Table2[Building ID wo B0],0))
Ajax H.S. | 8111-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 5 | 13
Alexander Graham Bell P.S. | 10250-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
Altona Forest P.S. | 10251-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 20 | 13
Anderson C & VI | 5478-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 71 | 13
Applecroft P.S. | 5349-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 8 | 13
Bayview Heights P.S. | 5392-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 20 | 13
Beau Valley P.S. | 5398-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 27 | 13
Beaver River P.S. | 5399-2 | Mechanical Ventilation | Yes | Yes | Yes | Yes | No | 0 | 13
Bellwood P.S. | 5410-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 14 | 13
Biidaasige Mandamin P.S. | 6681-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 13 | 13
Blair Ridge P.S. | 12175-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 8 | 13
Bobby Orr P.S. | 11117-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 13 | 13
Bolton C. Falby P.S. | 8111-2 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 12 | 13
Brock H.S. | 8141-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 7 | 13
Brooklin H.S. | 19299-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 46 | 13
Brooklin Village P.S. | 11190-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 13 | 13
C.E. Broughton P.S. | 5478-2 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 7 | 13
Cadarackque P.S. | 5481-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 17 | 13
Captain Michael Vandenbos P.S. | 10399-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Carruthers Creek P.S. | 11107-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 15 | 13
Cartwright Central P.S. | 5550-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 8 | 13
Chris Hadfield P.S. | 19027-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 18 | 13
Clara Hughes P.S. | 5719-2 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 25 | 13
Claremont P.S. | 6456-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 15 | 13
College Hill P.S. | 5613-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 15 | 13
Colonel J.E. Farewell P.S. | 5610-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 17 | 13
Coronation P.S. | 5635-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 7 | 13
da Vinci P.S. | 18071-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 25 | 13
David Bouchard P.S. | 5226-2 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 13 | 13
Donald A. Wilson S.S. | 11113-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Dr. C.F. Cannon P.S. | 6133-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 10 | 13
Dr. Robert Thornton P.S. | 5706-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 27 | 13
Dr. Roberta Bondar P.S. | 5707-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 13 | 13
Dr. S.J. Phillips P.S. | 5708-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 9 | 13
Duffin's Bay P.S. | 5320-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 12 | 13
Dunbarton H.S. | 6938-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 17 | 13
Dunbarton HS - South Campus | 6938-2 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 0 | 13
Durham Alternative S.S. (DASS - Oshawa) | 8577-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 0 | 13
Durham Alternative S.S. (DASS - Pickering) | 20163-1 | Mechanical Ventilation | NA | NA | NA | NA | NA | 12 | 13
EA Lovell School - ACEC (DCE) | 5734-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 36 | 13
Eagle Ridge P.S. | 11118-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 21 | 13
Earl A. Fairman P.S. | 5732-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Eastdale C & VI | 5186-2 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 24 | 13
Elizabeth B. Phin P.S. | 6624-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 17 | 13
Elsie MacGill P.S. | 19579-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 21 | 13
Fairport Beach P.S. | 5810-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 20 | 13
Fallingbrook P.S. | 10256-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Forest View P.S. | 5916-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 14 | 13
Frenchmans Bay P.S. | 5859-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 38 | 13
G.L. Roberts C & VI | 5574-2 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 14 | 13
Gandatsetiagon P.S. | 5866-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Glen Dhu P.S. | 5877-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 19 | 13
Glen Street P.S. | 5889-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 20 | 13
Glengrove P.S. | 5894-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 20 | 13
Goodwood P.S. | 6805-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 18 | 13
Gordon B. Attersley P.S. | 10257-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Greenbank P.S. | 6565-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 20 | 13
Harmony Heights P.S. | 5964-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 13 | 13
Henry Street H.S. | 8245-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 6 | 13
Highbush P.S. | 5934-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 15 | 13
Hillsdale P.S. | 6007-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 6 | 13
J. Clarke Richardson C.I. | 10322-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 20 | 13
Jack Miner P.S. | 10397-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 21 | 13
Jeanne Sauvé P.S. | 19481-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 7 | 13
John Dryden P.S. | 6068-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 18 | 13
Joseph Gould P.S. | 6082-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Josiah Henson P.S. | 30066-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | No | 0 | 13
Julie Payette P.S. | 12261-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 12 | 13
Kedron P.S. | 5638-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
Lakeside P.S. | 6139-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 20 | 13
Lakewoods P.S. | 5574-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 12 | 13
Lester B. Pearson P.S. | 6161-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 13 | 13
Lincoln Alexander P.S. | 6168-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 24 | 13
Lincoln Avenue P.S. | 6167-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
Maamawi iyaawag P.S. | 20497-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | No | 0 | 13
Maple Ridge P.S. | 6208-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 11 | 13
Mary Street Community School | 6254-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
Maxwell Heights S.S. | 12126-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 11 | 13
McCaskill's Mills P.S. | 12047-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
Meadowcrest P.S. | 6271-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 7 | 13
Michaëlle Jean P.S. | 19300-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 15 | 13
Norman G. Powers P.S. | 11192-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Northern Dancer P.S. | 19578-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 15 | 13
Nottingham P.S. | 11191-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 22 | 13
O'Neill C & VI | 8325-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 14 | 13
Ontario Street P.S. | 6185-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 11 | 13
Ormiston P.S. | 6408-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 17 | 13
Pickering H.S. | 8338-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 25 | 13
Pierre Elliot Trudeau P.S. | 10477-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Pine Ridge S.S. | 8339-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 9 | 13
Port Perry H.S. | 8344-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 36 | 13
Prince Albert P.S. | 6564-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 8 | 13
Pringle Creek P.S. | 6520-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 8 | 13
Quaker Village P.S. | 10258-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 14 | 13
Queen Elizabeth P.S. | 6537-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
R.H. Cornish P.S. | 6482-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 38 | 13
R.S. McLaughlin C & VI | 5314-2 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 22 | 13
Robert Munsch P.S. | 12177-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 6 | 13
Roland Michener P.S. | 6605-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 17 | 13
Romeo Dallaire P.S. | 12174-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 14 | 13
Rosebank Road P.S. | 6613-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Rosemary Brown P.S. | 19775-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 6 | 13
S.A. Cawker P.S. | 6669-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Scott Central P.S. | 6651-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 25 | 13
Seneca Trail P.S. | 19028-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 18 | 13
Sherwood P.S. | 11012-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
Sinclair S.S. | 8367-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 6 | 13
Sir Samuel Steele P.S. | 10398-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Sir William Stephenson P.S. | 11189-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 13 | 13
Southwood Park P.S. | 6711-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 19 | 13
Stephen G. Saywell P.S. | 6732-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 20 | 13
Sunderland P.S. | 6747-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Sunset Heights P.S. | 6752-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 24 | 13
Terry Fox P.S. | 10478-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Trillium Woods P.S. | 20375-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | No | 0 | 13
Uxbridge P.S. | 6804-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 25 | 13
Uxbridge S.S. | 8408-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 2 | 13
Valley Farm P.S. | 6811-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 17 | 13
Valley View P.S. | 6808-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Vaughan Willard P.S. | 6814-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 13 | 13
Village Union P.S. | 8330-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 15 | 13
Vimy Ridge P.S. | 12176-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 9 | 13
Vincent Massey P.S. | 5186-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 16 | 13
Viola Desmond P.S. | 19577-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 29 | 13
Walter E. Harris P.S. | 5546-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 16 | 13
Waverly P.S. | 6869-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 31 | 13
West Lynde P.S. | 6197-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 8 | 13
Westcreek P.S. | 10259-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 19 | 13
Westney Heights P.S. | 6881-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 16 | 13
Whitby Shores P.S. | 12238-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 27 | 13
William Dunbar P.S. | 6915-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 20 | 13
Williamsburg P.S. | 12020-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 18 | 13
Willows Walk P.S. | 19776-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 10 | 13
Winchester P.S. | 10260-1 | Mechanical Ventilation | Yes | Yes | Yes | Yes | NA | 18 | 13
Woodcrest P.S. | 6934-1 | Partial Mechanical Ventilation | Yes | Yes | Yes | Yes | Yes | 7 | 13
| 136 | [5 empty] | Total deployed in Schools on report = | 2161
ABSENT FROM PUBLIC VIEW REPORT:
[7 empty] | Thorah Central (closed) 5560-1 = | 23
**Lincoln Ave - check back with Pat in October to see if it's fully ventilated. | [6 empty] | Ed Centre (Office) 8367-1 = | 30
[7 empty] | Maintenance (Office) 11584-1 = | 24
[7 empty] | Duffins Creek (Oudoor Ed Centre) 30142-1 = | 3
[7 empty] | Durham Forest (Oudoor Ed Centre) 30141-1 = | 10
[7 empty] | Nonquon (Outdoor Ed Centre) 19982-1 = | 0
[7 empty] | Total in OTHER LOCATIONS in eBASE = | 90
[7 empty] | GRAND TOTAL DEPLOYED/In Storage at MC= | 2251
[7 empty] | PURCHASED UNITS = | 2586
[7 empty] | Not accounted for = | 335

## Vent Project Details (hidden)
Project Number | Project Name | Project Organization | Project Manager | Construction Start Date | Construction Completion Date | Incl. In Prev. Year on tab 5
20251577 | 2025 - Library/Office Cooling Stations - Hillsdale PS | Hillsdale P.S. | Patrick Cook | 2024-09-03 | 2026-01-30 | Reported as 2024/2025 | 2024/25 - Only 8 projects reported
20241520 | 2024 - Air Conditioning System - Sinclair SS | Sinclair S.S. | Aruna Ajitkumar Rajinidevi | 2025-01-06 | 2025-03-26 | Do not include - very small project, limited scope | 1. Dunbarton HS – Main Campus - Dust collector replacement
20251572 | 2025 - Air Conditioning System - DASS-Simcoe | Durham Alternative S.S.-Oshawa | Patrick Cook | 2025-03-01 | 2025-09-07 | Reported as 2024/2025 | 2. Dunbarton HS – South Campus – Ventilation upgrade phase 1
20251543 | 2025 - Ventilation & A/C Upgrade - Scott Central PS | Scott Central P.S. | Patrick Cook | 2025-03-01 | 2025-12-31 | Reported as 2024/2025 | 3. J.Clarke Richardson CVI – Chiller replacement
20251556 | 2025 - Dust Collector - Brock HS | Brock H.S. | Stewart Osinga | 2025-07-01 | 2025-12-31 | Reported as 2024/2025 | 4. Scott Central PS – Ventilation upgrade (new)
20241436 | 2024 - Ventilation Upgrades - Wood Shops - Dunbarton HS | Dunbarton H.S. | Chris Thaler | 2025-07-02 | 2026-01-31 | Reported as 2024/2025 | 5. DASS Simcoe – Air conditioning
20251554 | 2025 - Interior Renovations - RH Cornish PS | R.H. Cornish P.S. | Michael Kennedy | 2025-03-07 | 2026-03-30 | Reported as 2024/2025 | 6. Hillsdale PS – Library, office, & SERT air conditioning
| 2026 - Ventilation & Controls Upgrade Ph 1 - Dunbarton HS - South Campus | Dunbarton HS - South Campus |  |  |  | Phase I Reported as 2024/2025
20251541 | 2025 - HVAC - Air Conditioning System - J Clarke Richardson Col. | J.Clarke Richardson Collegiate | Patrick Cook | 2025-10-13 | 2026-05-29 | Reported as 2024/2025 | 7. R.H. Cornish PS – Gym to classrooms conversion including RTU replacement
20251598 | 2025 - Ventilation - Dunbarton HS | Dunbarton H.S. | Patrick Cook | 2025-10-16 | 2027-08-31 | Reported as 2025/2026 | 8. Brock HS – Dust Collector Replacement
20261073 | 2026 - Cooling Tower Repairs - Pine Ridge SS | Pine Ridge S.S | Patrick Cook | 2026-01-01 | 2026-08-31 | Reported as 2025/2026
20261061 | 2026 - HVAC Upgrade - Brock HS | Brock H.S. | Patrick Cook | 2026-01-01 | 2026-08-31 | (**Under Rewview, may cancel/postpone) Reported as 2025/2026 for now | Not sure if we are adding windows, but, if so, the following projects apply:
20261058 | 2026 - Office Air Conditioning - Ormiston PS | Ormiston P.S. | Patrick Cook | 2026-01-01 | 2026-08-31 | Reported as 2025/2026 | 9. Port Perry HS – Phase 4 – Original building window replacement
20261017 | 2026 - HVAC & AHU Replacement - Vaughan Willard PS | Vaughan Willard P.S. | Patrick Cook | 2026-01-23 | 2026-09-30 | Reported as 2025/2026 | 10. Ajax HS – 1954, 62, 63 additions window replacements
20261018 | 2026 - HVAC - Ventilation & DHW Replacement - Lincoln Avenue PS | Lincoln Avenue P.S. | Patrick Cook | 2026-02-20 | 2026-09-25 | Reported as 2025/2026
20251618 | 2025 - HVAC A/C Upgrade - Culinary Arts - Eastdale CVI | Eastdale C.V.I. | Patrick Cook | 2026-03-13 | 2026-08-28 | Reported as 2025/2026
20261075 | 2026 - HVAC Upgrades - Bolton C Falby PS | Bolton C. Falby P.S. | Patrick Cook | 2026-04-01 | 2026-08-31 | Do not include - investigation only
20261011 | 2026 - Ventilation & Controls Upgrade Ph 2 - Dunbarton HS - South Campus | Dunbarton HS - South Campus | Patrick Cook | 2026-04-01 | 2026-09-26 | Phase II Reported as 2025/2026
20261012 | 2026 - Dust Collector Replacement - Ajax HS | Ajax H.S. | Patrick Cook | 2026-06-29 | 2026-09-30
20261016 | 2026 - Dust Collector - O'Neill CVI | O'Neill C.V.I. | Patrick Cook | 2026-06-29 | 2026-09-30 | Reported as 2025/2026
20261034 | 2026 - Ventilation - Dust Collector - Anderson CVI | Anderson C.V.I. | Patrick Cook | 2026-06-29 | 2026-09-30 | Reported as 2025/2026
2024/2025
2025/2026

## HEPA Count by ID (hidden)
ID Code | Building ID wo B0 | Count of Equipment #
10250-B01 | 10250-1 | 19
10251-B01 | 10251-1 | 20
10256-B01 | 10256-1 | 10
10257-B01 | 10257-1 | 10
10258-B01 | 10258-1 | 14
10259-B01 | 10259-1 | 19
10260-B01 | 10260-1 | 18
10322-B01 | 10322-1 | 20
10397-B01 | 10397-1 | 21
10398-B01 | 10398-1 | 16
10399-B01 | 10399-1 | 16
10477-B01 | 10477-1 | 16
10478-B01 | 10478-1 | 10
11012-B01 | 11012-1 | 19
11107-B01 | 11107-1 | 15
11113-B01 | 11113-1 | 10
11117-B01 | 11117-1 | 13
11118-B01 | 11118-1 | 21
11189-B01 | 11189-1 | 13
11190-B01 | 11190-1 | 13
11191-B01 | 11191-1 | 22
11192-B01 | 11192-1 | 10
11584-B01 | 11584-1 | 24
12020-B01 | 12020-1 | 18
12047-B01 | 12047-1 | 19
12126-B01 | 12126-1 | 11
12174-B01 | 12174-1 | 14
12175-B01 | 12175-1 | 8
12176-B01 | 12176-1 | 9
12177-B01 | 12177-1 | 6
12238-B01 | 12238-1 | 27
12261-B01 | 12261-1 | 12
18071-B01 | 18071-1 | 25
19027-B01 | 19027-1 | 18
19028-B01 | 19028-1 | 18
19299-B01 | 19299-1 | 46
19300-B01 | 19300-1 | 15
19481-B01 | 19481-1 | 7
19577-B01 | 19577-1 | 29
19578-B01 | 19578-1 | 15
19579-B01 | 19579-1 | 21
19775-B01 | 19775-1 | 6
19776-B01 | 19776-1 | 10
20163-B01 | 20163-1 | 12
30141-B01 | 30141-1 | 10
30142-B01 | 30142-1 | 3
5186-B01 | 5186-1 | 16
5186-B02 | 5186-2 | 24
5226-B02 | 5226-2 | 13
5314-B01 | 5314-1 | 21
5314-B02 | 5314-2 | 22
5320-B01 | 5320-1 | 12
5349-B01 | 5349-1 | 8
5392-B01 | 5392-1 | 20
5398-B01 | 5398-1 | 27
5410-B01 | 5410-1 | 14
5478-B01 | 5478-1 | 71
5478-B02 | 5478-2 | 7
5481-B01 | 5481-1 | 17
5546-B01 | 5546-1 | 16
5550-B01 | 5550-1 | 8
5560-B01 | 5560-1 | 23
5574-B01 | 5574-1 | 12
5574-B02 | 5574-2 | 14
5610-B01 | 5610-1 | 17
5613-B01 | 5613-1 | 15
5635-B01 | 5635-1 | 7
5638-B01 | 5638-1 | 19
5706-B01 | 5706-1 | 27
5707-B01 | 5707-1 | 13
5708-B01 | 5708-1 | 9
5719-B02 | 5719-2 | 25
5732-B01 | 5732-1 | 16
5734-B01 | 5734-1 | 36
5810-B01 | 5810-1 | 20
5859-B01 | 5859-1 | 38
5866-B01 | 5866-1 | 16
5877-B01 | 5877-1 | 19
5889-B01 | 5889-1 | 20
5894-B01 | 5894-1 | 20
5916-B01 | 5916-1 | 14
5934-B01 | 5934-1 | 15
5964-B01 | 5964-1 | 13
6007-B01 | 6007-1 | 6
6068-B01 | 6068-1 | 18
6082-B01 | 6082-1 | 16
6133-B01 | 6133-1 | 10
6139-B01 | 6139-1 | 20
6161-B01 | 6161-1 | 13
6167-B01 | 6167-1 | 19
6168-B01 | 6168-1 | 24
6185-B01 | 6185-1 | 11
6197-B01 | 6197-1 | 8
6208-B01 | 6208-1 | 11
6254-B01 | 6254-1 | 19
6271-B01 | 6271-1 | 7
6408-B01 | 6408-1 | 17
6456-B01 | 6456-1 | 15
6482-B01 | 6482-1 | 38
6520-B01 | 6520-1 | 8
6537-B01 | 6537-1 | 19
6564-B01 | 6564-1 | 8
6565-B01 | 6565-1 | 20
6605-B01 | 6605-1 | 17
6613-B01 | 6613-1 | 16
6624-B01 | 6624-1 | 17
6651-B01 | 6651-1 | 25
6669-B01 | 6669-1 | 10
6681-B01 | 6681-1 | 13
6711-B01 | 6711-1 | 19
6732-B01 | 6732-1 | 20
6747-B01 | 6747-1 | 10
6752-B01 | 6752-1 | 24
6804-B01 | 6804-1 | 25
6805-B01 | 6805-1 | 18
6808-B01 | 6808-1 | 10
6811-B01 | 6811-1 | 17
6814-B01 | 6814-1 | 13
6869-B01 | 6869-1 | 31
6881-B01 | 6881-1 | 16
6915-B01 | 6915-1 | 20
6934-B01 | 6934-1 | 7
6938-B01 | 6938-1 | 17
8111-B01 | 8111-1 | 5
8111-B02 | 8111-2 | 12
8141-B01 | 8141-1 | 7
8245-B01 | 8245-1 | 6
8325-B01 | 8325-1 | 14
8330-B01 | 8330-1 | 15
8338-B01 | 8338-1 | 25
8339-B01 | 8339-1 | 9
8344-B01 | 8344-1 | 36
8367-B01 | 8367-1 | 6
8408-B01 | 8408-1 | 2
Grand Total | Grand Total | 2251

## Portable Count by ID (hidden)
School with Portables | Count of Equipment # | ID
Adelaide Mclaughlin PS | 3 | 5314-1
Alexander Graham Bell PS | 4 | 10250-1
Altona Forest PS | 4 | 10251-1
Anderson CVI | 7 | 5478-1
Applecroft PS | 2 | 5349-1
Beau Valley PS | 1 | 5398-1
Beaver River PS | 4 | 5399-2
Bellwood PS | 4 | 5410-1
Bolton C. Falby PS | 1 | 8111-2
Brock HS | 2 | 8141-1
Brooklin HS | 3 | 19299-1
Brooklin Village PS | 2 | 11190-1
C.E. Broughton PS | 9 | 5478-2
Cadarackque PS | 2 | 5481-1
Captain Michael VandenBos PS | 10 | 10399-1
Carruthers Creek PS | 1 | 11107-1
Clara Hughes PS | 10 | 5719-2
Claremont PS | 5 | 6456-1
College Hill PS | 4 | 5613-1
Colonel J.E. Farewell PS | 1 | 5610-1
Coronation PS | 5 | 5635-1
da Vinci PS | 4 | 18071-1
Donald A. Wilson SS | 3 | 11113-1
Dr. S.J. Phillips PS | 3 | 5708-1
Duffins Creek - Environmental Education Centre | 3 | 30142-1
Dunbarton HS | 1 | 6938-1
Durham Forest - Environmental Education Centre | 2 | 30141-1
E.A. Fairman PS | 4 | 5732-1
Eagle Ridge PS | 3 | 11118-1
Eastdale CVI | 17 | 5186-2
Elsie MacGill PS | 4 | 19579-1
Fallingbrook PS | 11 | 10256-1
Forest View PS | 3 | 5916-1
Gandatsetiagon PS | 5 | 5866-1
Goodwood PS | 1 | 6805-1
Gordon B. Attersley PS | 4 | 10257-1
Harmony Heights PS | 4 | 5964-1
Henry Street HS | 12 | 8245-1
J.Clarke Richardson Collegiate | 18 | 10322-1
Jack Miner PS | 8 | 10397-1
Jeanne Sauvé PS | 2 | 19481-1
John Dryden PS | 3 | 6068-1
Joseph Gould PS | 2 | 6082-1
Josiah Henson PS | 8 | 30066-1
Kedron PS | 10 | 5638-1
Lincoln Alexander PS | 2 | 6168-1
Lincoln Avenue PS | 5 | 6167-1
Maamawi iyaawag PS (prev #115) | 6 | 20497-1
Maintenance Centre | 6 | 11584-1
Maple Ridge PS | 5 | 6208-1
Mary Street Community School | 3 | 6254-1
Maxwell Heights SS | 20 | 12126-1
McCaskill’s Mills PS | 3 | 12047-1
Nonquon - Environmental Education Centre | 1 | 19982-1
Norman G. Powers PS | 6 | 11192-1
Northern Dancer PS | 10 | 19578-1
Ormiston PS | 7 | 6408-1
Pickering HS | 7 | 8338-1
Pierre Elliott Trudeau PS | 8 | 10477-1
Port Perry HS | 1 | 8344-1
Prince Albert PS | 2 | 6564-1
Pringle Creek PS | 8 | 6520-1
Queen Elizabeth PS | 5 | 6537-1
R.H. Cornish PS | 1 | 6482-1
R.S. McLaughlin CVI | 9 | 5314-2
Robert Munsch PS | 3 | 12177-1
Roméo Dallaire PS | 2 | 12174-1
Rosebank Road PS | 3 | 6613-1
S.A. Cawker PS | 4 | 6669-1
Scott Central PS | 2 | 6651-1
Seneca Trail PS | 1 | 19028-1
Sherwood PS | 7 | 11012-1
Sinclair SS | 19 | 8367-1
Sir Samuel Steele PS | 2 | 10398-1
Sir William Stephenson PS | 5 | 11189-1
Southwood Park PS | 2 | 6711-1
Sunderland PS | 5 | 6747-1
Sunset Heights PS | 10 | 6752-1
Terry Fox PS | 4 | 10478-1
Trillium Woods PS | 7 | 20375-1
Uxbridge SS | 2 | 8408-1
Valley View PS | 3 | 6808-1
Vaughan Willard PS | 2 | 6814-1
Vimy Ridge PS | 2 | 12176-1
Vincent Massey PS | 7 | 5186-1
Viola Desmond PS | 8 | 19577-1
Waverly PS | 5 | 6869-1
West Lynde PS | 7 | 6197-1
William Dunbar PS | 7 | 6915-1
Williamsburg PS | 9 | 12020-1
Willows Walk PS | 3 | 19776-1
Woodcrest PS | 7 | 6934-1
School on Ministry List | School ID | # of Portables
Adelaide Mclaughlin P.S. | 5314-1 | Yes
Ajax H.S. | 8111-1 | NA
Alexander Graham Bell P.S. | 10250-1 | Yes
Altona Forest P.S. | 10251-1 | Yes
Beau Valley P.S. | 5398-1 | Yes
Applecroft P.S. | 5349-1 | Yes
Bayview Heights P.S. | 5392-1 | NA
Earl A. Fairman P.S. | 5732-1 | Yes
Beaver River P.S. | 5399-2 | Yes
Bellwood P.S. | 5410-1 | Yes
Biidaasige Mandamin P.S. | 6681-1 | NA
Blair Ridge P.S. | 12175-1 | NA
Bobby Orr P.S. | 11117-1 | NA
Bolton C. Falby P.S. | 8111-2 | Yes
Greenbank P.S. | 6565-1 | NA
Brooklin H.S. | 19299-1 | Yes
Brooklin Village P.S. | 11190-1 | Yes
C.E. Broughton P.S. | 5478-2 | Yes
Cadarackque P.S. | 5481-1 | Yes
Captain Michael Vandenbos P.S. | 10399-1 | Yes
Carruthers Creek P.S. | 11107-1 | Yes
Cartwright Central P.S. | 5550-1 | NA
Chris Hadfield P.S. | 19027-1 | NA
Clara Hughes P.S. | 5719-2 | Yes
Anderson C & VI | 5478-1 | Yes
College Hill P.S. | 5613-1 | Yes
Colonel J.E. Farewell P.S. | 5610-1 | Yes
Coronation P.S. | 5635-1 | Yes
da Vinci P.S. | 18071-1 | Yes
David Bouchard P.S. | 5226-2 | NA
Donald A. Wilson S.S. | 11113-1 | Yes
Dr. C.F. Cannon P.S. | 6133-1 | NA
Dr. Robert Thornton P.S. | 5706-1 | NA
Dr. Roberta Bondar P.S. | 5707-1 | NA
Brock H.S. | 8141-1 | Yes
Duffin's Bay P.S. | 5320-1 | NA
Dunbarton H.S. | 6938-1 | Yes
Dunbarton HS - South Campus | 6938-2 | NA
Durham Alternative S.S. (DASS - Oshawa) | 8577-1 | NA
Durham Alternative S.S. (DASS - Pickering) | 20163-1 | NA
Claremont P.S. | 6456-1 | Yes
Eagle Ridge P.S. | 11118-1 | Yes
Dr. S.J. Phillips P.S. | 5708-1 | Yes
EA Lovell School - ACEC (DCE) | 5734-1 | NA
Elizabeth B. Phin P.S. | 6624-1 | NA
Elsie MacGill P.S. | 19579-1 | Yes
Eastdale C & VI | 5186-2 | Yes
Fallingbrook P.S. | 10256-1 | Yes
Forest View P.S. | 5916-1 | Yes
Fairport Beach P.S. | 5810-1 | NA
G.L. Roberts C & VI | 5574-2 | NA
Gandatsetiagon P.S. | 5866-1 | Yes
Glen Dhu P.S. | 5877-1 | NA
Glen Street P.S. | 5889-1 | NA
Glengrove P.S. | 5894-1 | NA
Goodwood P.S. | 6805-1 | Yes
Gordon B. Attersley P.S. | 10257-1 | Yes
Frenchmans Bay P.S. | 5859-1 | NA
Harmony Heights P.S. | 5964-1 | Yes
Henry Street H.S. | 8245-1 | Yes
Highbush P.S. | 5934-1 | NA
Hillsdale P.S. | 6007-1 | NA
J. Clarke Richardson C.I. | 10322-1 | Yes
Jack Miner P.S. | 10397-1 | Yes
Jeanne Sauvé P.S. | 19481-1 | Yes
John Dryden P.S. | 6068-1 | Yes
Joseph Gould P.S. | 6082-1 | Yes
Josiah Henson P.S. | 30066-1 | Yes
Julie Payette P.S. | 12261-1 | NA
Kedron P.S. | 5638-1 | Yes
Lakeside P.S. | 6139-1 | NA
Lakewoods P.S. | 5574-1 | NA
Lester B. Pearson P.S. | 6161-1 | NA
Lincoln Alexander P.S. | 6168-1 | Yes
Lincoln Avenue P.S. | 6167-1 | Yes
Maamawi iyaawag P.S. | 20497-1 | Yes
Maple Ridge P.S. | 6208-1 | Yes
Mary Street Community School | 6254-1 | Yes
Maxwell Heights S.S. | 12126-1 | Yes
McCaskill's Mills P.S. | 12047-1 | Yes
Meadowcrest P.S. | 6271-1 | NA
Michaëlle Jean P.S. | 19300-1 | NA
Norman G. Powers P.S. | 11192-1 | Yes
Northern Dancer P.S. | 19578-1 | Yes
Nottingham P.S. | 11191-1 | NA
O'Neill C & VI | 8325-1 | NA
Ontario Street P.S. | 6185-1 | NA
Ormiston P.S. | 6408-1 | Yes
Pickering H.S. | 8338-1 | Yes
Pierre Elliot Trudeau P.S. | 10477-1 | Yes
Pine Ridge S.S. | 8339-1 | NA
Port Perry H.S. | 8344-1 | Yes
Prince Albert P.S. | 6564-1 | Yes
Pringle Creek P.S. | 6520-1 | Yes
Quaker Village P.S. | 10258-1 | NA
Queen Elizabeth P.S. | 6537-1 | Yes
R.H. Cornish P.S. | 6482-1 | Yes
R.S. McLaughlin C & VI | 5314-2 | Yes
Robert Munsch P.S. | 12177-1 | Yes
Roland Michener P.S. | 6605-1 | NA
Romeo Dallaire P.S. | 12174-1 | Yes
Rosebank Road P.S. | 6613-1 | Yes
Rosemary Brown P.S. | 19775-1 | NA
S.A. Cawker P.S. | 6669-1 | Yes
Scott Central P.S. | 6651-1 | Yes
Seneca Trail P.S. | 19028-1 | Yes
Sherwood P.S. | 11012-1 | Yes
Sinclair S.S. | 8367-1 | Yes
Sir Samuel Steele P.S. | 10398-1 | Yes
Sir William Stephenson P.S. | 11189-1 | Yes
Southwood Park P.S. | 6711-1 | Yes
Stephen G. Saywell P.S. | 6732-1 | NA
Sunderland P.S. | 6747-1 | Yes
Sunset Heights P.S. | 6752-1 | Yes
Terry Fox P.S. | 10478-1 | Yes
Trillium Woods P.S. | 20375-1 | Yes
Uxbridge P.S. | 6804-1 | NA
Uxbridge S.S. | 8408-1 | Yes
Valley Farm P.S. | 6811-1 | NA
Valley View P.S. | 6808-1 | Yes
Vaughan Willard P.S. | 6814-1 | Yes
Village Union P.S. | 8330-1 | NA
Vimy Ridge P.S. | 12176-1 | Yes
Vincent Massey P.S. | 5186-1 | Yes
Viola Desmond P.S. | 19577-1 | Yes
Walter E. Harris P.S. | 5546-1 | NA
Waverly P.S. | 6869-1 | Yes
West Lynde P.S. | 6197-1 | Yes
Westcreek P.S. | 10259-1 | NA
Westney Heights P.S. | 6881-1 | NA
Whitby Shores P.S. | 12238-1 | NA
William Dunbar P.S. | 6915-1 | Yes
Williamsburg P.S. | 12020-1 | Yes
Willows Walk P.S. | 19776-1 | Yes
Winchester P.S. | 10260-1 | NA
Woodcrest P.S. | 6934-1 | Yes

## Board Ventilation Strate-PY (hidden)
Index | Board ID | Ventilation Strategy | Board Name
1 | 31 | calibrate HVAC systems for increased air flow and fresh air intake | Huron-Superior Catholic District School Board
2 | 31 | utilize MERV 13 filters and increase frequency of change-out | Huron-Superior Catholic District School Board
3 | 31 | operate ventilation system 2 hours before and after occupancy | Huron-Superior Catholic District School Board
4 | 31 | place HEPA filtration units in non-ventilated and FDK spaces | Huron-Superior Catholic District School Board
1 | 10 | All ventilation systems at LKDSB schools have been assessed to prioritize improvements. | Lambton Kent District School Board
2 | 10 | Ventilation systems have been modified to increase the amount of incoming fresh air and have been programmed to operate longer hours to ensure occupied spaces have full air exchanges before, during and after class time. | Lambton Kent District School Board
3 | 10 | Stand-alone HEPA filtration units are being positioned in all occupied kindergarten classrooms and all other occupied classrooms which do not have access to mechanical ventilation systems. | Lambton Kent District School Board
4 | 10 | HEPA filter units will also be provided in libraries, gyms, staff rooms and offices where mechanical ventilation is not available. | Lambton Kent District School Board
1 | 56 | Utiliser des filtres de la plus haute qualité possible | Conseil scolaire public du Nord-Est de l'Ontario
2 | 56 | Procéder à de fréquents changements de filtres tout au long de l’année scolaire | Conseil scolaire public du Nord-Est de l'Ontario
3 | 56 | Faire fonctionner les systèmes de ventilation deux heures ou plus avant et après l’occupation de l’école | Conseil scolaire public du Nord-Est de l'Ontario
4 | 56 | Calibrer les systèmes de chauffage, de ventilation et de climatisation pour un débit d’air maximal et une entrée d’air frais accrue | Conseil scolaire public du Nord-Est de l'Ontario
1 | 103 | Use the highest-grade filters possible, preferably MERV 13 (Minimum Efficiency Reporting Value), and undertake frequent filter changes throughout the school year | Penetanguishene Protestant Separate School Board
2 | 103 | Place standalone air cleaner/HEPA (High Efficiency Particulate Air) filter units in every occupied Full-Day Kindergarten (FDK) classroom as an additional health and safety measure | Penetanguishene Protestant Separate School Board
3 | 103 | Calibrate HVAC (Heating, Ventilation and Air Conditioning) systems for maximum air flow and increased outdoor air intake | Penetanguishene Protestant Separate School Board
4 | 103 | Operate ventilation systems 2 hours or more before and after school occupancy | Penetanguishene Protestant Separate School Board
1 | 59 | Se conformer aux exigences ministérielles en matière de ventilation. | Conseil des écoles publiques de l'Est de l'Ontario
2 | 59 | Optimiser la qualité de l’air dans nos écoles par une maintenance accrue des systèmes de ventilation et de filtration ou par l'ajout d'appareils de filtration mobiles. | Conseil des écoles publiques de l'Est de l'Ontario
3 | 59 | Maximiser l'apport d'air frais en augmentant le taux de changement d'air pour les écoles avec ventilation mécanique ou par l'ouverture des fenêtres aux écoles sans ventilation mécanique. | Conseil des écoles publiques de l'Est de l'Ontario
4 | 59 | Identifier et exécuter des projets d'installation ou d'amélioration de ventilation dans ses écoles. | Conseil des écoles publiques de l'Est de l'Ontario
1 | 24 | Upgrade all HVAC filters to MERV 13 or highest-grade filter possible and change 5 times per year | Waterloo Region District School Board
2 | 24 | Assess and fine tune all Mechanical Ventilation systems Board wide as well as maximize fresh air intake and minimize recirculation air in all HVAC systems | Waterloo Region District School Board
3 | 24 | Execute Mechanical Ventilation upgrade projects in all teaching and non-teaching spaces where required. | Waterloo Region District School Board
4 | 24 | Install HEPA units in all teaching and non-teaching spaces without Mechanical Ventilation plus Install HEPA units in all FDK rooms and ACE classrooms | Waterloo Region District School Board
1 | 42 | Upgrade HVAC filtration to MERV13 and ensure optimal operation of outdoor air intakes and components | York Catholic District School Board
2 | 42 | Install HEPA filters in areas of school where less than optimal ventilation assessed and in Kindergarten classrooms | York Catholic District School Board
3 | 42 | Increase the openings of outdoor air dampers and flush the buildings prior and post occupancy with outdoor air | York Catholic District School Board
4 | 42 | Add CO2 sensors to monitor the IAQ (Indoor Air Quality) and retrocommission HVAC and Building Automation Systems for optimal ventilation | York Catholic District School Board
1 | 33A | Use the highest grade filters possible, preferably MERV 13 | Northwest Catholic District School Board
2 | 33A | Undertake frequent filter changes throughout the year | Northwest Catholic District School Board
3 | 33A | Operate ventilation systems 2 hrs or more before and after school occupancy and calibrate HVAC systems for maximum air flow and increased fresh air intake | Northwest Catholic District School Board
4 | 33A | Install HEPA filters in all classrooms or learning environments without mechanical ventilation as well as FDK classrooms at a minimum | Northwest Catholic District School Board
1 | 66 | Tous les systèmes de ventilation ont été évalués et remis au point afin d'optimiser la circulation de l'air et les horaires de fonctionnement ont été ajustés pour les faire fonctionner plus longtemps | Conseil scolaire de district catholique du Centre-Est de l'Ontario
2 | 66 | Des filtres de qualité supérieure sont utilisés, dont les filtres ayant la cote MERV-13 et ces filtres sont remplacés plus fréquemment | Conseil scolaire de district catholique du Centre-Est de l'Ontario
3 | 66 | L'entrée d'air frais des systèmes CVC a été accrue | Conseil scolaire de district catholique du Centre-Est de l'Ontario
4 | 66 | Des unités de filtration HEPA autonomes ont été placées dans tous les locaux sans fenêtre qui ouvre vers l'extérieur, les locaux avec systèmes de ventilation moins performants, les classes mobiles et les classes de maternelle et jardin d'enfants | Conseil scolaire de district catholique du Centre-Est de l'Ontario
1 | 26 | The UCDSB past practice is to use the highest rated filters possible in our ventilation systems, and we will continue to do that in addition to more frequent changing of filters. | Upper Canada District School Board
2 | 26 | Daily monitoring of controls to verify ventilation systems are operating to maintain maximum level of ventilation in occupied areas and temperatures are controlled. | Upper Canada District School Board
3 | 26 | HEPA units will be in places such as portables, classes where windows can’t open, and other places where air flow can’t be increased by the school’s mechanical ventilation system. | Upper Canada District School Board
4 | 26 | Fresh airflow will be increased during the day and all ventilation systems will operate for two hours before and after school use. | Upper Canada District School Board
1 | 53 | Enhanced maintenance and commissioning of ventilation equipment at all OCSB schools | Ottawa Catholic District School Board
2 | 53 | Capital investments to replace aging rooftop mechanical equipment | Ottawa Catholic District School Board
3 | 53 | Installation of 225 unit ventilators in portable classrooms to provide fresh air ventilation and air conditioning | Ottawa Catholic District School Board
4 | 53 | Installation of ceiling circulation fans in classrooms which incorporate UV-C light technology | Ottawa Catholic District School Board
1 | 5B | All schools with mechanical ventilation have MERV 13 filters installed. Routine maintenance including regular filter replacements every 2 months will continue to be completed. | Rainy River District School Board
2 | 5B | All schools that do not have Energy Recover Ventilators as part of the mechanical ventilation system will have portable HEPA units in each classroom. | Rainy River District School Board
3 | 5B | All JK/SK classes will have a portable HEPA unit in each classroom. | Rainy River District School Board
4 | 5B | Air exchanges have been increased in schools without Energy Recover Ventilators until cold weather dictates. To increase natural ventilation, windows will be opened, where possible. | Rainy River District School Board
1 | 41 | the Board is taking steps to ensure that the heating, ventilation and air conditioning (HVAC) systems within the schools are in optimum condition. | Peterborough Victoria Northumberland and Clarington Catholic DSB
2 | 41 | Where possible all filters have been upgraded to a MERV 13 filter and increased frequency of filter changes | Peterborough Victoria Northumberland and Clarington Catholic DSB
3 | 41 | Mechanical ventilation is being added to areas that previosuly did not have it. | Peterborough Victoria Northumberland and Clarington Catholic DSB
4 | 41 | Extended hours and maximum fresh air is being brought into the schools where possible | Peterborough Victoria Northumberland and Clarington Catholic DSB
1 | 34B | Bring all of our systems to meet ASHRAE 62.1 guidelines which increases our fresh air supply to all classrooms. | Superior North Catholic District School Board
2 | 34B | Ultraviolet light air purifying for all our air handling systems which removes all pathogens from the air stream. | Superior North Catholic District School Board
3 | 34B | Upgrade all filters to Merv13 or better which increases the effectiveness of filtration in the air stream. | Superior North Catholic District School Board
4 | 34B | Running ventilation systems longer during the school day which ensures sufficient fresh air is coming into the school. | Superior North Catholic District School Board
1 | 61 | Prolonger l'horaire de fonctionnement des systèmes pour que la ventilation fonctionne 2 heures avant le début et 2 heures après les classes | Conseil scolaire de district catholique du Nouvel-Ontario
2 | 61 | Ajustement des points de consignes qui ont pour effet d'augmenter l'apport d'air frais (p.ex. augmenter la position minimale des volets d'air frais, diminuer le point de consigne pour le CO2) | Conseil scolaire de district catholique du Nouvel-Ontario
3 | 61 | Remplacer les filtres des systèmes de ventilation par des filtres MERV 13 | Conseil scolaire de district catholique du Nouvel-Ontario
4 | 61 | Ouvrir les fenêtres autant que possible et tel que toléré selon la température extérieure | Conseil scolaire de district catholique du Nouvel-Ontario
1 | 34A | Scheduling of ventilation system has been adjusted to start up 2 hours prior to the opening of school and to run for 2 hours after school is out. | Thunder Bay Catholic District School Board
2 | 34A | All filters in Air Handling Units have been changed to Merv 13 wherever possible, if the unit will not fit a Merv 13, we would go to a Merv, 12 or 11 and so on. | Thunder Bay Catholic District School Board
3 | 34A | Duct cleaning has been complete for all schools, on both the supply and return sides. | Thunder Bay Catholic District School Board
4 | 34A | Stand alone HEPA air purifiers will be placed in all JK/SK classrooms. | Thunder Bay Catholic District School Board
1 | 21 | Ventilation systems are to be inspected and in good working order prior to the start of the school. Any ventilation issues that arise throughout the school year will be addressed immediately. | Hamilton-Wentworth District School Board
2 | 21 | Ventilation system filters have been upgraded and increased frequency of filter changes will be conducted throughout the school year. | Hamilton-Wentworth District School Board
3 | 21 | Ventilation systems will operate 2 hours before and after school occupancy. | Hamilton-Wentworth District School Board
4 | 21 | Ventilation systems were calibrated to increase fresh air intake and classrooms are recommended to open windows to maximize ventilation rates. | Hamilton-Wentworth District School Board
1 | 63 | Entretien préventif et évaluation des systèmes mécaniques de ventilation en place qui sont effectués par des personnes qualifiées. | Conseil scolaire catholique Providence
2 | 63 | Mise en place des pratiques exemplaires pour optimiser la qualité de l'air. | Conseil scolaire catholique Providence
3 | 63 | Les classes maternelles et jardins sont toutes munis d'unités portatives de filtration d'air. | Conseil scolaire catholique Providence
4 | 63 | Utilisation de filtres performants et remplacements fréquents. | Conseil scolaire catholique Providence
1 | 16 | Ventilate schools with maximum outdoor air 2 hours before and after school occupancy. | York Region District School Board
2 | 16 | HVAC systems are operating at maximum allowable outdoor air without affecting space comfort. | York Region District School Board
3 | 16 | MERV-13 filters have been installed in all schools with mechanical ventilation systems. | York Region District School Board
4 | 16 | Standalone portable HEPA air purifier units have been installed in all teaching spaces without mechanical ventilation and kindergarten classrooms. | York Region District School Board
1 | 38 | Two mechanical ventilation verification engineering reports completed, August 2020 and August 2021 ensuring all HVAC systems are operational and meet Ministry mandated requirements. | London District Catholic School Board
2 | 38 | All building schedules increased two hours before and after school. Maximum HVAC fresh air intake verified for current building design at all schools/buildings. | London District Catholic School Board
3 | 38 | Merv 13 Filters added to all sites with a monthly change frequency. HEPA units added in all FDK/KG classrooms, older non-leased portables and under-ventilated areas at some schools. | London District Catholic School Board
4 | 38 | Externally audited PM program has been in place to ensure all mechanical ventilation equipment is operational and inspected by certified technicians. | London District Catholic School Board
1 | 14 | The engagement of a 3rd party HVAC consulting firm for immediate direction and the development of a 5 year infrastructure investment plan. | Kawartha Pine Ridge District School Board
2 | 14 | Upgrade all existing central HVAC systems from a MERV 5 filter media to MERV 13. | Kawartha Pine Ridge District School Board
3 | 14 | Activate central HVAC systems earlier in the morning to exchange all building air with fresh outside air before students and staff arrive. Increase the fresh air during school hours. | Kawartha Pine Ridge District School Board
4 | 14 | Deploy over 1200 standalone HEPA filter units (MERV 17) to school spaces that do not have a current, central HVAC system. | Kawartha Pine Ridge District School Board
1 | 9 | Air filtration units have been installed in all teaching and office spaces with only natural or exhaust ventilation | Greater Essex County District School Board
2 | 9 | Forced air ventilation systems in all school operate from 4:30 am until 5:30 pm to ensure buildings are flushed out prior to the start of school. MERV 13 filters are being used in all systems with regular filter changes. | Greater Essex County District School Board
3 | 9 | Outside Air has been maximized in all forced air ventilation units while ensuring occupant comfort. | Greater Essex County District School Board
4 | 9 | All schools with natural or exhaust ventilation only will receive forced air ventilation systems prior to December 31, 2021. These spaces will use air filtration units until this work is complete. | Greater Essex County District School Board
1 | 60A | Maximiser la santé et la sécurité de tous en assurant une qualité de l'air optimale | Conseil scolaire de district catholique des Grandes Rivières
2 | 60A | Augmenter la quantité d'air frais | Conseil scolaire de district catholique des Grandes Rivières
3 | 60A | Augmenter la filtration de l'air | Conseil scolaire de district catholique des Grandes Rivières
4 | 60A | Augmenter la fréquence des inspections | Conseil scolaire de district catholique des Grandes Rivières
1 | 60B | Assurer le bon fonctionnement des systèmes de ventilation mécanique en continue avec son programme d’inspection et de maintenance préventive des équipements CVAC, et d'effectuer les réparations nécessaires dans un délai raisonnable. | Conseil scolaire de district catholique Franco-Nord
2 | 60B | Mise à niveau de la filtration des équipements mécaniques qui recycle l’air intérieur et l’ajout des unités de filtration HEPA dans les locaux qui ne sont pas munies d'équipements CVAC. | Conseil scolaire de district catholique Franco-Nord
3 | 60B | Opérer les systèmes de ventilation mécanique deux heures avant l’arrivée des élèves et deux heures après leur départ afin d’assurer un échange d’aire des locaux. | Conseil scolaire de district catholique Franco-Nord
4 | 60B | Ouvrir les fenêtres plus fréquemment, en considérant la santé et sécurité des occupants et de la température extérieure. | Conseil scolaire de district catholique Franco-Nord
1 | 29 | Preventive maintenance inspection/service program on all mechanical units to ensure continued effective operation of ventilation equipment (including operating windows). If something breaks down it is acted on very quickly through our in-house staff and if necessary external contractors to ensure reduced downtime. | Hastings and Prince Edward District School Board
2 | 29 | Filters are changed more frequently and the filter rating increased to catch smaller particles, as appopriate for each type of equipment. | Hastings and Prince Edward District School Board
3 | 29 | Ventilation equipment has been updated or added to schools to provide a long term solution to increased air quality, and adjusted to do a 2-hour purge pre and post the school day. | Hastings and Prince Edward District School Board
4 | 29 | Standalone HEPA units placed in all Kindergarten classrooms and all occupied learning spaces without mechanical ventilation, as per the Ministry of Education's guidelines for school ventilation. | Hastings and Prince Edward District School Board
1 | 28 | Increase fresh air flow through duct sealing and increased run times | Renfrew County District School Board
2 | 28 | Provide air treatment systems (in duct and stand alone) | Renfrew County District School Board
3 | 28 | Implement recommended Best Practices for Daily Checks and Monthly Maintenance on Ventilation Equipment | Renfrew County District School Board
4 | 28 | Increase number of filter changes | Renfrew County District School Board
1 | 23 | InDuct Air Purification Systems in Schools with HVAC | Grand Erie District School Board
2 | 23 | Increased Filter Changes and System Checks | Grand Erie District School Board
3 | 23 | New Mechanical Ventilation Units in Spaces without HVAC | Grand Erie District School Board
4 | 23 | Portable Air Filtration Units in Spaces without HVAC | Grand Erie District School Board
1 | 25 | Since the pandemic began, we have been very active in ensuring the school's environment is safe for the staff and students. Our engineers have consulted with the HVAC professionals and public health organizations to ensure we are following their guidance. | Ottawa-Carleton District School Board
2 | 25 | Initially, all HVAC systems were recommissioned and correct operation was verified. Repairs were completed as required. Our inventory of system type in each school was updated. | Ottawa-Carleton District School Board
3 | 25 | With the goal of optimizing air quality, we focussed on two areas: increasing ventilation rates and increasing filtration. All schools have received upgrades dependant on the particulars at each site. | Ottawa-Carleton District School Board
4 | 25 | To supplement the HVAC systems, HEPA and UV filtration equipment has been installed in areas and rooms that may benefit from this equipment. We continue to monitor air quality and enhance HVAC systems to improve the indoor learning environments. | Ottawa-Carleton District School Board
1 | 39 | Increased mechanical air filtration to highest-grade possible | St. Clair Catholic District School Board
2 | 39 | Inspect air filters and mechanical equipment monthly | St. Clair Catholic District School Board
3 | 39 | Keep mechanical ventilation systems running longer (pre and post occupancy) | St. Clair Catholic District School Board
4 | 39 | Increase outdoor air ventilation and bypss energy recovery systems | St. Clair Catholic District School Board
1 | 27 | Implement additional filter changes for increased and improved air flow and air quality in all filtered HVAC units. | Limestone District School Board
2 | 27 | Adjust building automation programing to increase HVAC run times from two hours before the building is occupied to two hours after the building has been vacated to increase the “flushing” of the air within the building. | Limestone District School Board
3 | 27 | Adjust, where possible, the damper opening to increase the amount of fresh air that is supplied through the HVAC unit. | Limestone District School Board
4 | 27 | Complete operational audits on all the HVAC units within the schools via contractors. The deficiencies noted will be rectified in a timely manner for school start-up. | Limestone District School Board
1 | 65 | Investissements en capital pour l'amélioration des systèmes de ventilation et l'ajout d'unités de filtration (par exemple HEPA). | Conseil scolaire de district catholique de l'Est ontarien
2 | 65 | Augmentation de fréquence de changement de filtres et utilisation de filtres de la plus haute performance. | Conseil scolaire de district catholique de l'Est ontarien
3 | 65 | Évaluation et calibration des systèmes de chauffage, de ventilation et de climatisation pour un débit d’air maximal et une admission d’air frais accrue. | Conseil scolaire de district catholique de l'Est ontarien
4 | 65 | Fonctionnement des systèmes de ventilation plus longtemps avant et après l’occupation de l’école. | Conseil scolaire de district catholique de l'Est ontarien
1 | 49 | Ventilation - Replacement and/or upgrades of roof top units, unit ventilators, heat pumps, exhaust systems, boilers and BAS systems in several schools. | Waterloo Catholic District School Board
2 | 49 | Place stand alone HEPA Units in all FDK classrooms as well as stand alone UV units in all internal classroom spaces including libraries and Spec. Ed. Classrooms. | Waterloo Catholic District School Board
3 | 49 | Filtration - upgrade filters to MERV13 rating where possible. Develop a preventative maintenance program to regularly inspect and replace filters to maintain overall performance. | Waterloo Catholic District School Board
4 | 49 | Increase fresh air exchanges in all classrooms by running systems 2 hours prior to student entry and 2 hours after end of school day wherever possible. | Waterloo Catholic District School Board
1 | 1 | Upgrading or providing mechnical ventilation per assessment and increasing runtime of mechanical ventilation before and after school hours | District School Board Ontario North East
2 | 1 | Providing stand alone or wall mount HEPA Filtration units in rooms where mechanical ventilation is absent | District School Board Ontario North East
3 | 1 | Increasing fresh air intake through opening windows or mechanical ventilation | District School Board Ontario North East
4 | 1 | Duct cleaning or duct sealing; providing in-line duct filtration in all schools that have ductwork | District School Board Ontario North East
1 | 3 | Schools have been survey to determine the ventilation requirements. Rooms with no ventilation or mandated rooms (FDK), have received a HEPA unit as in accordance with the Standardized Ventilation Measure Report. | Rainbow District School Board
2 | 3 | All existing units have been re-commissioned and filters have been changed. RDSB have developed a routine monthly preventative maintenance schedule and checklist. | Rainbow District School Board
3 | 3 | Ensure ventilation systems are operating properly and provide acceptable indoor air quality for the occupancy load in each classroom | Rainbow District School Board
4 | 3 | RDSB will continue to attribute a 25% of it's Capital Allocation towards ventilation | Rainbow District School Board
1 | 17 | Comprehensive system-wide recommissioning and enhanced maintenance of all HVAC equipment including cleaning, servicing, inspection and repair of all air handling equipment/components. | Simcoe County District School Board
2 | 17 | Provision of additional ventilation by running systems longer, monitoring/adjusting outside air in response to indoor CO2 levels and additional outside air/air exchanges. | Simcoe County District School Board
3 | 17 | Installation of new HVAC systems in portions of 5 schools that previously did not have mechanical ventilation to achieve mechanical ventilation in 100% of learning spaces board wide. | Simcoe County District School Board
4 | 17 | Installation of HEPA filtration units in all Kindergarten classrooms, as well as learning spaces without mechanical ventilation pending the completion of the new HVAC capital projects (noted in item 3). | Simcoe County District School Board
1 | 50 | Maximize fresh air intake on all mechanical systems (24/7 operation) and windows open where possible. | Niagara Catholic District School Board
2 | 50 | Increased frequency of filter changes (every two months) | Niagara Catholic District School Board
3 | 50 | Provision of portable HEPA air purifiers in all facilities. | Niagara Catholic District School Board
4 | 50 | Recommissioning of all mechanical systems in schools. | Niagara Catholic District School Board
1 | 44 | Assurance: All schools have mechanical ventilation systems. Saint Mary’s Catholic School in Huntsville will have upgrades completed for the fall 2021. Overall system capability and function was confirmed through a re-commissioning project including air balancing for all SMCDSB HVAC systems as of August 31, 2021. All critical repairs to ensure optimal ventilation will be completed by school start-up. | Simcoe Muskoka Catholic District School Board
2 | 44 | Enhancement: Work continues to enhance system reliability and resiliency through third party re-commissioning funded through the Optimising Air Quality and Ventilation funding. Eighteen investment projects at various facilities (16 schools and 2 board office locations) consisting of HVAC equipment replacements and window replacements are ongoing. Nine projects have an anticipated completion of August 31, 2021 and 9 projects have an anticipated completion by December 31, 2021; these projects are funded through Federal Investing in Canada Infrastructure Program, COVID-19 Resilience Infrastructure (CVRIS) initiative and the SMCDSB renewal program. | Simcoe Muskoka Catholic District School Board
3 | 44 | Operating & Maintenance Practices: In alignment with Ministry of Education Guidelines, MERV13 filters have been installed in all SMCDSB facilities. Operating and maintenance procedures have been reviewed and updated for routine maintenance, inspections, and operating strategies. | Simcoe Muskoka Catholic District School Board
4 | 44 | Monitoring & Response: Monitoring of building mechanical ventilation through sophisticated automation systems to ensure optimal airflow for all spaces and to proactively respond to ventilation challenges. Air Purification(HEPA) Units have been purchased through Provincial funding and will be installed in all Kindergarten classrooms by school start up and a contingency inventory of units will be available for dispatch if needed. | Simcoe Muskoka Catholic District School Board
1 | 13 | ENHANCE PERFORMANCE: Increase the minimum ventilation rate on all HVAC systems, including a full air exchange post and pre occupied times. Recommission all pneumatic controls and existing HVAC systems to maintain optimal performance. | Durham District School Board
2 | 13 | INCREASE EQUIPMENT/MATERIALS: Purchase 870 portable HEPA air filtration units (The Ministry of Education has supplied an additional 311 units). Invest in upgraded filters from MERV 7 to MERV 13 for all ventilation systems. | Durham District School Board
3 | 13 | MONITOR & VERIFY: Complete a system ventilation check in every building. Recalibrate systems to optimize air flow within each building. Monitor building automation systems daily for any HVAC related issues. | Durham District School Board
4 | 13 | PREVENTATIVE MAINTENANCE: Increase filter change frequency. Utilize duct cleaning services to aid in the efficiency of ventilation systems and to enhance air quality. | Durham District School Board
1 | 6A | Maximize the ventilation settings in all of our facilities with current infrastructure. | Lakehead District School Board
2 | 6A | Filtering the air. | Lakehead District School Board
3 | 6A | Maximizing outdoor air. | Lakehead District School Board
4 | 6A | Continue to invest capital funds for the upgrade of HVAC systems throughout the board facilities. | Lakehead District School Board
1 | 100 | Increase Frequency of HVAC Filter Changes | James Bay Lowlands Secondary School Board
2 | 100 | Addition of Classroom Standalone HEPA Filtration Units | James Bay Lowlands Secondary School Board
3 | 100 | Increased Fresh Air Intake (Opening of Windows) | James Bay Lowlands Secondary School Board
4 | 100 | Recalibrate HVAC System to allow for Higher Grade Filters When Able to Secure Vendor | James Bay Lowlands Secondary School Board
1 | 18 | Follow best practices in assessing, maintaining and upgrading ventilation and air filtration systems, including increased frequency of filter changes and running systems two hours before/after occupancy. | Upper Grand District School Board
2 | 18 | The UGDSB increased our standard filter to MERV 10 prior to COVID. The board will use the highest grade filters compatible with HVAC units, including MERV 13 where possible. | Upper Grand District School Board
3 | 18 | In addition to placing HEPA filtration units in all Ministry required learning spaces (i.e., JK/SK classrooms), UGDSB will place additional units in all classrooms in Grades 1-8 and all life skills (Developmentally Delayed) classes in elementary and secondary. | Upper Grand District School Board
4 | 18 | As an additional measure, conduct carbon dioxide (CO2) testing in learning spaces as a measure of ensuring ventilation systems are working properly in schools. | Upper Grand District School Board
1 | 22 | Increase Fresh Air Volumes | District School Board of Niagara
2 | 22 | Increase Ventilation Operating times | District School Board of Niagara
3 | 22 | Increase filter change frequency | District School Board of Niagara
4 | 22 | Add HEPA Filtration as required | District School Board of Niagara
1 | 46 | Continue best practice maintenance with a focus on equipment that impacts indoor air quality and increase air filtration to MERV 13, where possible. | Halton Catholic District School Board
2 | 46 | Increase outside air flow to occupied space where possible and run ventilation systems 2 hours before and after occupancy to flush buildings daily. | Halton Catholic District School Board
3 | 46 | Rebalance HVAC systems to maximize ventilation air into occupied spaces. | Halton Catholic District School Board
4 | 46 | Use Portable HEPA air cleaners in high risk areas identified by the Ministry of Education. | Halton Catholic District School Board
1 | 32 | To have all ventilation systems inspected and in good working order prior to the start of the school year. | Sudbury Catholic District School Board
2 | 32 | To use the highest grade filters possible, with a preference to use Merv 13 and to undertake frequent filter changes throughout the year. | Sudbury Catholic District School Board
3 | 32 | To operate ventilation systems 2 hours before and after school and to calibrate HVAC systems for increased fresh air. | Sudbury Catholic District School Board
4 | 32 | To upgrade all locations with natural ventilation to a full ventilation system. | Sudbury Catholic District School Board
1 | 35 | All ventilation systems inspected and in good working order | Bruce-Grey Catholic District School Board
2 | 35 | Use highest grade filters possible | Bruce-Grey Catholic District School Board
3 | 35 | Increased Fresh Air intake and run systems longer | Bruce-Grey Catholic District School Board
4 | 35 | Install HEPA standalone units in JK SK Spaces | Bruce-Grey Catholic District School Board
1 | 57 | Ajouter de la ventilation mécanique dans les écoles qui ne sont pas équipées à 100 % avec de la ventilation mécanique | Conseil scolaire public du Grand Nord de l’Ontario
2 | 57 | Augmenter la fréquence de remplacement des filtres dans les unités de ventilation et utiliser des filtres de meilleure qualité. | Conseil scolaire public du Grand Nord de l’Ontario
3 | 57 | Augmenter le nombre d'heures par jour que les unités de ventilation fonctionnent. | Conseil scolaire public du Grand Nord de l’Ontario
4 | 57 | Ajouter des unités de purificateur d'air dans chaque salle de classe en utilisation et dans certains autres locaux. | Conseil scolaire public du Grand Nord de l’Ontario
1 | 37 | All ventilation systems have undergone a thorough internal review to ensure they are operating properly. | Windsor-Essex Catholic District School Board
2 | 37 | All systems will be operated in "occupied mode" for a period of one week prior to the return of students. | Windsor-Essex Catholic District School Board
3 | 37 | The Board has improved filtration in all mechanically ventilated space by changing from MERV 8 to MERV 13 filters. The filter change frequency has increased from quarterly to monthly. | Windsor-Essex Catholic District School Board
4 | 37 | The Board has installed portable HEPA filtration units for interior spaces without mechanical ventilation. All JK/SK and Daycare rooms have also been equipmed with portable HEPA filtration units. | Windsor-Essex Catholic District School Board
5 | 37 | The Board has opened fresh air dampers (to improve the outside air dilution rate) as much as possible without compromising equipment systems or occupant comfort. Occupancy schedules have been set to commence two hours prior to program start and end two hours after programs have concluded. | Windsor-Essex Catholic District School Board
6 | 37 | School Exhaust fans have been reviewed and fans in poor condition have been replaced with direct drive, variable speed fans. These fans are much quieter and allow for increased volume when needed. | Windsor-Essex Catholic District School Board
1 | 30B | Implement portable air filtration systems with high-efficiency particulate air (HEPA) filters for classrooms and other occupied spaces that have limited air ventilation/fresh air options. | Nipissing-Parry Sound Catholic District School Board
2 | 30B | Increase the frequency in which filters are replaced to ensure maximum airflow. | Nipissing-Parry Sound Catholic District School Board
3 | 30B | Upgrade current air filters to MERV 13 to improve air filtaration. | Nipissing-Parry Sound Catholic District School Board
4 | 30B | Install new mechanical rooftop ventilation systems which will serve classrooms and other occupied spaces. | Nipissing-Parry Sound Catholic District School Board
1 | 58 | Systèmes de ventilation vérifiés, fonctionnement démarre au moins 2 heures avant l'occupation et termine au moins 2 heures après la journée scolaire et l'apport d'air frais à été augmenté | Conseil scolaire Viamonde
2 | 58 | Tous les écoles atteignent ou dépassent les exigences du Ministère au sujet du nombre de ventilateurs portatifs HEPA dans les salles de classes et autres locaux partagés. | Conseil scolaire Viamonde
3 | 58 | Dans les écoles sans ventilation avec apport d'air frais, 2 unités de purification d'air sont en place dans chaque salle de classe. | Conseil scolaire Viamonde
4 | 58 | Plusieurs filtres dans les équipements de ventilation ont été remplacés par des filtres de calibre MERV-13. Tous les filtres des écoles sont changés régulièrement. | Conseil scolaire Viamonde
1 | 11 | Optimization of ventilation systems to increase the flow of outdoor/fresh air which includes extending operating hours of systems two hours before and after school day | Thames Valley District School Board
2 | 11 | Increased frequency of filter changes and utilization of highest MERV (Minimum Efficiency Reporting Value) rating where possible | Thames Valley District School Board
3 | 11 | Deployment of portable HEPA (High Efficiency Particulate Air) Filters to augment ventilation strategies at: Kindergarten classrooms; classrooms with students with complex medical and physical needs; learning environments in schools with passive ventilation | Thames Valley District School Board
4 | 11 | Continued capital investment to upgrade ventilation systems | Thames Valley District School Board
1 | 51 | ASHRAE Building Readiness and AHRAE 62.1 Guidelines | Brant Haldimand Norfolk Catholic District School Board
2 | 51 | Increased Ventilation | Brant Haldimand Norfolk Catholic District School Board
3 | 51 | Ventilation Control and Extended HVAC Operation | Brant Haldimand Norfolk Catholic District School Board
4 | 51 | Upgrading & Improving HVAC Filtration | Brant Haldimand Norfolk Catholic District School Board
1 | 52 | Optimize air quality systems at all facilities to ensure the health and safety for all CDSBEO students, staff, and partners. | Eastern Ontario Catholic District School Board
2 | 52 | Research and implement technologies to enhance our ventilation systems. | Eastern Ontario Catholic District School Board
3 | 52 | Utilize all resources at our disposal to improve our indoor air quality. | Eastern Ontario Catholic District School Board
4 | 52 | Continue frequent routine maintenance and inspections of our ventilation system to ensure optimal performance. | Eastern Ontario Catholic District School Board
1 | 47 | Maximize use of dedicated outdoor air supply systems (DOAS) for classrooms through long term investment decisions. | Hamilton-Wentworth Catholic District School Board
2 | 47 | Provide pre and post occupancy flushing of building air through central systems and to increase the proportion of fresh air intake where mechanically feasible. | Hamilton-Wentworth Catholic District School Board
3 | 47 | Adopt MERV-13 filters for all ventilation systems and to replace these quarterly. | Hamilton-Wentworth Catholic District School Board
4 | 47 | Perform scheduled preventive maintenance to and assess HVAC systems and equipment within all buildings on a monthly basis. | Hamilton-Wentworth Catholic District School Board
1 | 54 | Continue to optimize the air quality in classrooms and learning environments. | Renfrew County Catholic District School Board
2 | 54 | Improving air quality through the use of higher grade filters in school ventilation units and/or the use of portable HEPA units. | Renfrew County Catholic District School Board
3 | 54 | Additional maintenance, adjustments and filter changes throughout the Board. | Renfrew County Catholic District School Board
4 | 54 | Increase fresh air intake on HVAC units. | Renfrew County Catholic District School Board
1 | 8 | Projects undertaken over the summer of 2021 will address ventilation deficiencies in regular classrooms as identified by third party ventilation reviews. Until these projects are completed, portable HEPA filtration will be used as interim measure. | Avon Maitland District School Board
2 | 8 | HEPA filtration will be utilized, as directed by the Ministry of Education, in kindergarten classrooms. Additionally, HEPA filters will be employed in other teaching spaces and commons to augment existing ventilation as identified by third party reviews. | Avon Maitland District School Board
3 | 8 | Improved filters were installed in all HVAC units across the district at the start of the previous school year, September 2020. This strategy will continue for the 2021-2022 school year. | Avon Maitland District School Board
4 | 8 | Additional internal staff resources as well as external service companies are designated specifically to monitor and maintain filters and reliability for both permanently installed systems as well as portable HEPA filtration equipment. | Avon Maitland District School Board
1 | 43 | Filter Upgrades: the filters in ventilation equipment have been upgraded from MERV-10 to superior commercial grade MERV-13. The frequency of filter changes per year also incresed from 3 to 5 times. | Dufferin Peel Catholic District School Board
2 | 43 | Portable HEPA Filter Units: Over 1700 portable HEPA filte units have been deployed to schools. All FDK classrooms will receive HEPA units, as required by the Minitry of Education. | Dufferin Peel Catholic District School Board
3 | 43 | Extended Operating Ventilation Periods: The ventilation systems to are operated 2 hrs before and after school occupancy. In addition, ventilation will be run one week prior to reopening to flush the schools. | Dufferin Peel Catholic District School Board
4 | 43 | Enhanced Maintenance: DPCDSB’s in-house staff and the third-party consultants have performed HVAC inspections, repairs and adjustments to ensure mechanical systems are fully operational. | Dufferin Peel Catholic District School Board
1 | 48 | All schools are fully mechanically ventilated with MERV 13 filters in place. | Wellington Catholic District School Board
2 | 48 | Outside air intakes are set to optimize outdoor air and balance building comfort in heating and cooling season. | Wellington Catholic District School Board
3 | 48 | HVAC systems have been assessed including intake damper operation and preventative maintenance. | Wellington Catholic District School Board
4 | 48 | Ventilation will be started 2 hours before students arrive and operated 2 hours after students leave. | Wellington Catholic District School Board
1 | 2 | Ventilation Assements | Algoma District School Board
2 | 2 | Running Ventilation Equipment Longer (2 hrs prior and 2 hrs post) | Algoma District School Board
3 | 2 | Filters upraded to MERV 13 and changed more frequently | Algoma District School Board
4 | 2 | Increased fresh air intake based on occupancy | Algoma District School Board
1 | 15 | Upgrade Sites without supplied air to have designed supply/return air systems. | Trillium Lakelands District School Board
2 | 15 | Ensure systems' performance are optimized. | Trillium Lakelands District School Board
3 | 15 | Increase percentage of outdoor air within supply air systems to maximum amount (minimum 25% OA Damper positon) system permits while being able to maintain occupant comfort. | Trillium Lakelands District School Board
4 | 15 | Employ duct sealing and other strategies to increase airflow delivery to intended occupied space. | Trillium Lakelands District School Board
1 | 19 | Undertook retrofits, repairs or upgrades to provide immediate improvements to ventilation and air flow (units operating as designed, damper inspections, increased hours of operation, coil cleaning) | Peel District School Board
2 | 19 | Upgraded to MERV13 filters for mechanical ventilated systems and increased frequency of filter changes | Peel District School Board
3 | 19 | Supplied standalone HEPA units to all non-mechanically ventilated spaces as per Ministry guidelines | Peel District School Board
4 | 19 | Installation of Induct Air Treatment (UVC Technology) into all facilities with mechanical supply air systems | Peel District School Board
1 | 12 | Assess the condition of all ventilation systems and operable windows | Toronto District School Board
2 | 12 | Increase the operating hours of ventilation systems and maximize the intake of fresh air | Toronto District School Board
3 | 12 | Increase the frequency of air handler filter changes | Toronto District School Board
4 | 12 | Provide HEPA filtration units to all classrooms and instructional areas | Toronto District School Board
1 | 33B | Changed Buidling Automation System settings to run the ventialtion system 2 hours prior and after the facility occupancy | Kenora Catholic District School Board
2 | 33B | Increased frequency of filter changes and frequent monitoring of the ventialtion system | Kenora Catholic District School Board
3 | 33B | Increased the volume and frequency of outdoor fresh air intake and bypassed the conditioned air recircualtion | Kenora Catholic District School Board
4 | 33B | Installed stand alone HEPA units in areas of high transmission such as Kindergarten classrooms, Library, Cafeteria, Gym etc. | Kenora Catholic District School Board
1 | 40 | Installing Portable HEPA air purifiers in TCDSB schools to enhance air cleaning and ensuring filters in existing mechanical systems are replaced 4 times per year with the highest grade filter possible. | Toronto Catholic District School Board
2 | 40 | Conducting assessment on all mechanical systems to ensure they are fully operational, servicing where necessary and prioritizing repairs for ventilation systems. | Toronto Catholic District School Board
3 | 40 | Set mechanical systems to run at a maximum outside airflow a minimum of two hours before school starts and after it ends to refresh the air before arrival and remove particles at the end of the day. | Toronto Catholic District School Board
4 | 40 | Adjust operating schedules for all mechanical systems to maximize airflow, increase fresh air intake and increase the amount of air exchanges in the building per day. | Toronto Catholic District School Board
1 | 55 | All mechanical units have been and continue to be regularly assessed and serviced to optimize air flow | Algonquin and Lakeshore Catholic District School Board
2 | 55 | Filters for mechanical units have been upgraded, where possible, and the frequency of filter changes increased for improved air quality | Algonquin and Lakeshore Catholic District School Board
3 | 55 | Fresh air intake has been increased and the runtime of mechanical units have been lengthened, where possible | Algonquin and Lakeshore Catholic District School Board
4 | 55 | Standalone HEPA units have been placed as per the Ministry of Education guidelines for school ventilation, and as a minimum in all FDK classrooms and in all regular classroom environments. | Algonquin and Lakeshore Catholic District School Board
1 | 102 | HVAC Upgrade Project Approved and in Progress to Improve Air Quality and Ventilation at MPS | Moosonee District School Area Board
2 | 102 | Addition of Classroom Standalone HEPA Filtration Units | Moosonee District School Area Board
3 | 102 | Increased Fresh Air Intake (Opening of Windows) | Moosonee District School Area Board
4 | 102 | On-going Monitoring and Maintenance of Existing HVAC System | Moosonee District School Area Board
1 | 20 | Increased fresh air in schools by running ventilation equipment longer (pre and post occupancy air flushing), disabling energy recovery and efficiency technologies, and opening windows | Halton District School Board
2 | 20 | Upgraded all mechanical filtration to MERV-13 filters and changing every two months | Halton District School Board
3 | 20 | Install stand alone HEPA air purification devices in classrooms and other spaces that have limited pre-existing mechanical ventilation | Halton District School Board
4 | 20 | Upgraded mechanical ventilation systems in classrooms, gymnasiums, libraries, and portables using funding from CVRIS, school renewal, school condition improvement, and other board resources | Halton District School Board
1 | 4 | Conduct a gap analysis and ventilation assessment of all buildings within the Near North District School Board. | Near North District School Board
2 | 4 | Complete upgrades to existing mechanical ventilation located at some schools, to include: replacement of existing filters with MERV-13; installation of UV filtration; upgrades to existing ventilation and exhaust; and installation of additional air handling units. | Near North District School Board
3 | 4 | Implement solutions to address buildings with non-mechanical ventilation, to include: the purchase and deployment of portable HEPA filtration units in all classrooms; and service/repair of doors/windows. | Near North District School Board
4 | 4 | Continue to work with the Ministry of Education and Public Health authorities and implement changes as required to meet pandemic response requirements. | Near North District School Board
1 | 6B | Upgrades HVAC systems | Superior-Greenstone District School Board
2 | 6B | Increase air filtration and UV light disinfecting equipment | Superior-Greenstone District School Board
3 | 6B | Programming Building Automation Systems to remotely monitor HVAC (Heating, Ventilation, Air Conditioning) equipment, CO2 levels, VFD | Superior-Greenstone District School Board
4 | 6B | Enhance Preventative Maintenance, Testing, Commissioning Ventilation systems for all SGDSB Facilities | Superior-Greenstone District School Board
1 | 62 | Nos unités et systèmes de ventilation sont conformes aux exigences du guide de qualité de l'air intérieur ASHRAE, qui est recommandé par le MÉO. | Conseil scolaire de district catholique des Aurores boréales
2 | 62 | L'inspection de nos systèmes mécaniques est confiée à une tierce-partie. Nous recevons des rapports hebdomadaires et adressons les problèmes dans les plus brefs délais. | Conseil scolaire de district catholique des Aurores boréales
3 | 62 | Nos fournisseurs effectuent un changement des filtres MERV (au-delà de HEPA) ainsi que toutes les courroies pour optimiser la performance des systèmes. | Conseil scolaire de district catholique des Aurores boréales
4 | 62 | Les investissements se limitent aux édifices du CSDCAB. L'entretien des systèmes mécaniques dans nos écoles partagées est prise en charge par nos conseils partenaires, qui nous ont partagé leurs profils de ventilation. | Conseil scolaire de district catholique des Aurores boréales
1 | 7 | increased schedule/frequency for inspections and filter changes | Bluewater District School Board
2 | 7 | upgraded filters (Merv 13) in all HVAC equipment | Bluewater District School Board
3 | 7 | facility purging and operation of HVAC equipment 2 hours before and 2 hours after occupancy (at a minimum) | Bluewater District School Board
4 | 7 | operating HVAC equipment to optimize fresh air intake | Bluewater District School Board
1 | 101 | HVAC Filters upgraded to MERV Filters. | Moose Factory Island District School Area Board
2 | 101 | Utilize Exhausts where applicable. | Moose Factory Island District School Area Board
3 | 101 | Conduct Indoor Air Quality Assessments. | Moose Factory Island District School Area Board
4 | 101 | Open Office & Classroom windows where warranted. | Moose Factory Island District School Area Board

## Funding Tables (hidden)
The column titles for this worksheet are in rows 1 and 2. They span cells D1 through P1, and A2 through O2. The data spans cells A3 through P78. If you are not using a screen reader, you can press Alt + R, T for the Review Ribbon, Edit Comment to move to and open a Comment once you are on a cell with a Comment. When you are finished reading the Comment, press Escape to close the comment and return to the worksheet. If you are using the JAWS screen reader, press Ctrl + Shift + Apostrophe to get a list of Comments and their cell coordinates in the worksheet. Press Enter on the Comment you want to go to or Escape once you’ve read the Comment for a cell. You are returned to the workbook. Note that there is no keyboard command with JAWS to reread Comments or read Comments once you are on them in a cell. You must use the ability to list Comments in order to read them if you are using the JAWS screen reader. |  | Board DropDownList | Summer 2021 |  | 21-22 SY | [9 empty] | Board DropDownList | [5 empty] | X1000
Index | DSBNo | DSB Name | HVAC | Windows | HVAC | Windows | Total $ | Ventilation Funding | Windows Funding | Ventilation | SRA | Project Count | HEPA Units | Facilities with No Mechanical Ventilation | DSB Name | Aug 2020 $50M | Feb 2021 $50M | $29.4M for Filters | Funding for HEPA units | HEPA units | Hepa Funding (Approx. $ value for HEPA units provided) | Hepa Funding (Approx. $ value for HEPA units provided) | SRTCF Funding | ICIP-Ventilation Funding | HVAC System Type
1 | 1 | District School Board Ontario North East | [12 empty] | District School Board Ontario North East | 293100 | 293100 | 161908 | 18000 | 109 | 129160.5447 | 129161 | 268398 | 193307 | Mechanical Ventilation
2 | 2 | Algoma District School Board | [12 empty] | Algoma District School Board | 416400 | 416400 | 178138 | 28000 | 132 | 155381.1064 | 155381 | 323016 | 227876 | Partial Mechanical Ventilation
3 | 3 | Rainbow District School Board | [12 empty] | Rainbow District School Board | 449100 | 449100 | 208436 | 34000 | 900 | 271916.9362 | 271917 | 510593 | 327370 | Non-Mechanical Ventilation (Natural Ventilation / Exhaust Only)
4 | 4 | Near North District School Board | [12 empty] | Near North District School Board | 356200 | 356200 | 172157 | 3000 | 181 | 226273.7362 | 226274 | 411489 | 282901
5 | 5A | Keewatin-Patricia District School Board | [12 empty] | Keewatin-Patricia District School Board | 170900 | 170900 | 101339 | 13000 | 23 | 41758.6723 | 41759 | 107495 | 87815
6 | 5B | Rainy River District School Board | [12 empty] | Rainy River District School Board | 111400 | 111400 | 51128 | 8000 | 19 | 33989.617 | 33990 | 85994 | 68688
7 | 6A | Lakehead District School Board | [12 empty] | Lakehead District School Board | 293800 | 293800 | 122324 | 20000 | 26 | 47585.4638 | 47585 | 164466 | 129906
8 | 6B | Superior-Greenstone District School Board | [12 empty] | Superior-Greenstone District School Board | 148200 | 148200 | 62121 | 6000 | 10 | 26220.5617 | 26221 | 89867 | 68731
9 | 7 | Bluewater District School Board | [12 empty] | Bluewater District School Board | 452800 | 452800 | 264305 | 45000 | 103 | 131102.8085 | 131103 | 266574 | 207518
10 | 8 | Avon Maitland District School Board | [12 empty] | Avon Maitland District School Board | 402900 | 402900 | 256236 | 34000 | 62 | 93228.6638 | 93229 | 237936 | 186714
11 | 9 | Greater Essex County District School Board | [12 empty] | Greater Essex County District School Board | 846400 | 846400 | 483008 | 72000 | 491 | 519555.5745 | 519556 | 604347 | 436073
12 | 10 | Lambton Kent District School Board | [12 empty] | Lambton Kent District School Board | 678400 | 678400 | 321547 | 51000 | 320 | 350578.6213 | 350579 | 747340 | 519372
13 | 11 | Thames Valley District School Board | [12 empty] | Thames Valley District School Board | 1810200 | 1810200 | 1146633 | 201000 | 630 | 698243.8469 | 698244 | 1209330 | 908973
14 | 12 | Toronto District School Board | [12 empty] | Toronto District School Board | 6918600 | 6918600 | 3721149 | 527000 | 648 | 908008.3405 | 908008 | 5823125 | 3959828
15 | 13 | Durham District School Board | [7 empty] | 45.8787 | 15.39 | 54 | 2251 | #REF! | Durham District School Board | 1439500 | 1439500 | 999955 | 171000 | 311 | 374856.9192 | 374857 | 899094 | 671210
16 | 14 | Kawartha Pine Ridge District School Board | [12 empty] | Kawartha Pine Ridge District School Board | 882200 | 882200 | 479017 | 78000 | 933 | 954622.6724 | 954623 | 832483 | 582178
17 | 15 | Trillium Lakelands District School Board | [12 empty] | Trillium Lakelands District School Board | 532000 | 532000 | 267472 | 35000 | 768 | 779818.9277 | 779819 | 509333 | 357261
18 | 16 | York Region District School Board | [12 empty] | York Region District School Board | 2588000 | 2588000 | 1696047 | 282000 | 497 | 595303.8639 | 595304 | 1276193 | 993290
19 | 17 | Simcoe County District School Board | [12 empty] | Simcoe County District School Board | 1078400 | 1078400 | 718543 | 123000 | 149 | 208793.3617 | 208793 | 499402 | 417881
20 | 18 | Upper Grand District School Board | [12 empty] | Upper Grand District School Board | 845000 | 845000 | 485608 | 11000 | 262 | 398164.0851 | 398164 | 492669 | 375544
21 | 19 | Peel District School Board | [12 empty] | Peel District School Board | 2991300 | 2991300 | 2033872 | 417000 | 1462 | 1553811.064 | 1553811 | 1892163 | 1359560
22 | 20 | Halton District School Board | [12 empty] | Halton District School Board | 1239500 | 1239500 | 884175 | 155000 | 1045 | 1076014.1618 | 1076014 | 842069 | 626331
23 | 21 | Hamilton-Wentworth District School Board | [12 empty] | Hamilton-Wentworth District School Board | 1162000 | 1162000 | 673025 | 120000 | 794 | 826433.2597 | 826433 | 793548 | 611145
24 | 22 | District School Board of Niagara | [12 empty] | District School Board of Niagara | 1019300 | 1019300 | 538014 | 69000 | 428 | 470998.9788 | 470999 | 810095 | 594963
25 | 23 | Grand Erie District School Board | [12 empty] | Grand Erie District School Board | 764100 | 764100 | 367275 | 67000 | 765 | 786616.8511 | 786617 | 827338 | 538674
26 | 24 | Waterloo Region District School Board | [12 empty] | Waterloo Region District School Board | 1467400 | 1467400 | 863236 | 156000 | 331 | 389423.8979 | 389424 | 1034771 | 710793
27 | 25 | Ottawa-Carleton District School Board | [12 empty] | Ottawa-Carleton District School Board | 1681500 | 1681500 | 1073366 | 161000 | 780 | 836144.5788 | 836145 | 968614 | 739548
28 | 26 | Upper Canada District School Board | [12 empty] | Upper Canada District School Board | 860700 | 860700 | 438959 | 58000 | 147 | 191312.9873 | 191313 | 541141 | 419649
29 | 27 | Limestone District School Board | [12 empty] | Limestone District School Board | 568100 | 568100 | 313965 | 49000 | 820 | 833231.1831 | 833231 | 722400 | 538440
30 | 28 | Renfrew County District School Board | [12 empty] | Renfrew County District School Board | 284900 | 284900 | 172559 | 21000 | 63 | 82546.2128 | 82546 | 187020 | 137918
31 | 29 | Hastings and Prince Edward District School Board | [12 empty] | Hastings and Prince Edward District School Board | 447100 | 447100 | 250077 | 38000 | 199 | 286483.9149 | 286484 | 288292 | 210815
32 | 30A | Northeastern Catholic District School Board | [12 empty] | Northeastern Catholic District School Board | 102000 | 102000 | 42093 | 0 | 58 | 123333.7532 | 123334 | 178635 | 127317
33 | 30B | Nipissing-Parry Sound Catholic District School Board | [12 empty] | Nipissing-Parry Sound Catholic District School Board | 100900 | 100900 | 51728 | 8000 | 215 | 224331.4724 | 224331 | 159333 | 109628
34 | 31 | Huron-Superior Catholic District School Board | [12 empty] | Huron-Superior Catholic District School Board | 156700 | 156700 | 67410 | 11000 | 56 | 72834.8936 | 72835 | 150144 | 111558
35 | 32 | Sudbury Catholic District School Board | [12 empty] | Sudbury Catholic District School Board | 176400 | 176400 | 93118 | 14000 | 37 | 54383.3872 | 54383 | 100504 | 80125
36 | 33A | Northwest Catholic District School Board | [12 empty] | Northwest Catholic District School Board | 50700 | 50700 | 20789 | 6000 | 7 | 18451.5064 | 18452 | 23810 | 20300
37 | 33B | Kenora Catholic District School Board | [12 empty] | Kenora Catholic District School Board | 42900 | 42900 | 16799 | 4000 | 4 | 15538.1106 | 15538 | 23241 | 19854
38 | 34A | Thunder Bay Catholic District School Board | [12 empty] | Thunder Bay Catholic District School Board | 210300 | 210300 | 96697 | 18000 | 22 | 40787.5404 | 40788 | 108950 | 87236
39 | 34B | Superior North Catholic District School Board | [12 empty] | Superior North Catholic District School Board | 77700 | 77700 | 25886 | 5000 | 7 | 20393.7702 | 20394 | 47476 | 39064
40 | 35 | Bruce-Grey Catholic District School Board | [12 empty] | Bruce-Grey Catholic District School Board | 124500 | 124500 | 67335 | 2600 | 15 | 42729.8043 | 42730 | 68689 | 55030
41 | 36 | Huron-Perth Catholic District School Board | [12 empty] | Huron-Perth Catholic District School Board | 158300 | 158300 | 66229 | 13000 | 52 | 68950.366 | 68950 | 114830 | 87646
42 | 37 | Windsor-Essex Catholic District School Board | [12 empty] | Windsor-Essex Catholic District School Board | 454500 | 454500 | 283090 | 40000 | 167 | 191312.9873 | 191313 | 390603 | 268005
43 | 38 | London District Catholic School Board | [12 empty] | London District Catholic School Board | 523800 | 523800 | 303142 | 50000 | 69 | 101968.8511 | 101969 | 318080 | 248981
44 | 39 | St. Clair Catholic District School Board | [12 empty] | St. Clair Catholic District School Board | 227000 | 227000 | 125966 | 21000 | 75 | 94199.7958 | 94200 | 166436 | 124033
45 | 40 | Toronto Catholic District School Board | [12 empty] | Toronto Catholic District School Board | 2024700 | 2024700 | 1221920 | 203000 | 1766 | 1824756.8683 | 1824757 | 2043519 | 1419899
46 | 41 | Peterborough Victoria Northumberland and Clarington Catholic DSB | [12 empty] | Peterborough Victoria Northumberland and Clarington Catholic DSB | 367900 | 367900 | 211308 | 8000 | 39 | 95170.9277 | 95171 | 212374 | 173578
47 | 42 | York Catholic District School Board | [12 empty] | York Catholic District School Board | 1027000 | 1027000 | 697289 | 141000 | 499 | 543833.8724 | 543834 | 542858 | 437832
48 | 43 | Dufferin Peel Catholic District School Board | [12 empty] | Dufferin Peel Catholic District School Board | 1702200 | 1702200 | 1034393 | 131000 | 160 | 236956.1873 | 236956 | 743208 | 625298
49 | 44 | Simcoe Muskoka Catholic District School Board | [12 empty] | Simcoe Muskoka Catholic District School Board | 500400 | 500400 | 311761 | 55000 | 72 | 103911.1149 | 103911 | 255485 | 214379
50 | 45 | Durham Catholic District School Board | [12 empty] | Durham Catholic District School Board | 471100 | 471100 | 295396 | 47000 | 98 | 127218.2809 | 127218 | 321391 | 248496
51 | 46 | Halton Catholic District School Board | [12 empty] | Halton Catholic District School Board | 582000 | 582000 | 503317 | 77000 | 105 | 138871.8638 | 138872 | 265281 | 224478
52 | 47 | Hamilton-Wentworth Catholic District School Board | [12 empty] | Hamilton-Wentworth Catholic District School Board | 567800 | 567800 | 418581 | 70000 | 283 | 311733.3447 | 311733 | 410195 | 310638
53 | 48 | Wellington Catholic District School Board | [12 empty] | Wellington Catholic District School Board | 207000 | 207000 | 108067 | 20000 | 25 | 44672.0681 | 44672 | 110092 | 92149
54 | 49 | Waterloo Catholic District School Board | [12 empty] | Waterloo Catholic District School Board | 500800 | 500800 | 344326 | 20000 | 69 | 138871.8638 | 138872 | 276127 | 220731
55 | 50 | Niagara Catholic District School Board | [12 empty] | Niagara Catholic District School Board | 552300 | 552300 | 275261 | 57000 | 147 | 180630.5362 | 180631 | 301302 | 247209
56 | 51 | Brant Haldimand Norfolk Catholic District School Board | [12 empty] | Brant Haldimand Norfolk Catholic District School Board | 279800 | 279800 | 153358 | 24000 | 117 | 138871.8638 | 138872 | 223183 | 163694
57 | 52 | Eastern Ontario Catholic District School Board | [12 empty] | Eastern Ontario Catholic District School Board | 354400 | 354400 | 192184 | 30000 | 178 | 201024.3064 | 201024 | 229413 | 174348
58 | 53 | Ottawa Catholic District School Board | [12 empty] | Ottawa Catholic District School Board | 958500 | 958500 | 647137 | 87000 | 286 | 327271.4554 | 327271 | 723003 | 557084
59 | 54 | Renfrew County Catholic District School Board | [12 empty] | Renfrew County Catholic District School Board | 194800 | 194800 | 75459 | 14000 | 104 | 120420.3575 | 120420 | 238781 | 169635
60 | 55 | Algonquin and Lakeshore Catholic District School Board | [12 empty] | Algonquin and Lakeshore Catholic District School Board | 350400 | 350400 | 166326 | 9000 | 204 | 228216 | 228216 | 355897 | 241786
61 | 56 | Conseil scolaire public du Nord-Est de l'Ontario | [12 empty] | Conseil scolaire public du Nord-Est de l'Ontario | 69100 | 69100 | 52442 | 10000 | 16 | 32047.3532 | 32047 | 46696 | 40508
62 | 57 | Conseil scolaire public du Grand Nord de l’Ontario | [12 empty] | Conseil scolaire public du Grand Nord de l’Ontario | 149500 | 149500 | 77236 | 4600 | 36 | 61181.3106 | 61181 | 114511 | 84796
63 | 58 | Conseil scolaire Viamonde | [12 empty] | Conseil scolaire Viamonde | 509500 | 509500 | 230527 | 45000 | 67 | 100997.7192 | 100998 | 431210 | 308127
64 | 59 | Conseil des écoles publiques de l'Est de l'Ontario | [12 empty] | Conseil des écoles publiques de l'Est de l'Ontario | 390300 | 390300 | 266663 | 45000 | 192 | 214620.1532 | 214620 | 272722 | 213356
65 | 60A | Conseil scolaire de district catholique des Grandes Rivières | [12 empty] | Conseil scolaire de district catholique des Grandes Rivières | 336700 | 336700 | 124091 | 17000 | 170 | 190341.8553 | 190342 | 336249 | 224858
66 | 60B | Conseil scolaire de district catholique Franco-Nord | [12 empty] | Conseil scolaire de district catholique Franco-Nord | 107300 | 107300 | 63604 | 10000 | 69 | 83517.3447 | 83517 | 119045 | 79131
67 | 61 | Conseil scolaire de district catholique du Nouvel-Ontario | [12 empty] | Conseil scolaire de district catholique du Nouvel-Ontario | 370000 | 370000 | 119952 | 0 | 385 | 165092.4255 | 165092 | 358433 | 246583
68 | 62 | Conseil scolaire de district catholique des Aurores boréales | [12 empty] | Conseil scolaire de district catholique des Aurores boréales | 35800 | 35800 | 23341 | 5000 | 11 | 25249.4298 | 25249 | 38863 | 30744
69 | 63 | Conseil scolaire catholique Providence | [12 empty] | Conseil scolaire catholique Providence | 291500 | 291500 | 161917 | 17000 | 45 | 91286.4 | 91286 | 131534 | 110047
70 | 64 | Conseil scolaire catholique MonAvenir | [12 empty] | Conseil scolaire catholique MonAvenir | 541300 | 541300 | 264136 | 58000 | 97 | 133045.0724 | 133045 | 404356 | 300469
71 | 65 | Conseil scolaire de district catholique de l'Est ontarien | [12 empty] | Conseil scolaire de district catholique de l'Est ontarien | 370100 | 370100 | 197732 | 32000 | 116 | 138871.8638 | 138872 | 302440 | 217968
72 | 66 | Conseil scolaire de district catholique du Centre-Est de l'Ontario | [12 empty] | Conseil scolaire de district catholique du Centre-Est de l'Ontario | 562700 | 562700 | 365240 | 71000 | 203 | 234042.7915 | 234043 | 295506 | 234800
73 | 100 | James Bay Lowlands Secondary School Board | [12 empty] | James Bay Lowlands Secondary School Board | 5000 | 5000 | 13567 | 0 | 0 | #N/A |  | N/A | Funding not provided
74 | 101 | Moose Factory Island District School Area Board | [12 empty] | Moose Factory Island District School Area Board | 5000 | 5000 | 9242 | 0 | 20 | #N/A |  | N/A | Funding not provided
75 | 102 | Moosonee District School Area Board | [12 empty] | Moosonee District School Area Board | 5000 | 5000 | 4511 | 0 | 21 | #N/A |  | N/A | Funding not provided
76 | 103 | Penetanguishene Protestant Separate School Board | [12 empty] | Penetanguishene Protestant Separate School Board | 5000 | 5000 | 3844 | 1000 | 8 | #N/A |  | N/A | Funding not provided
77 | X1 | Campbell Children's School Authority | [12 empty] | Campbell Children's School Authority | 0 | 0 | N/A | 0 | 0 | #N/A |  | N/A | Funding not provided
78 | X2 | Bloorview School Authority | [12 empty] | Bloorview School Authority | 0 | 0 | N/A | 0 | 0 | #N/A |  | N/A | Funding not provided
79 | X3 | John McGivney Children's Centre School Authority | [12 empty] | John McGivney Children's Centre School Authority | 0 | 0 | N/A | 0 | 0 | #N/A |  | N/A | Funding not provided
80 | X4 | KidsAbility Education Authority | [12 empty] | KidsAbility Education Authority | 0 | 0 | N/A | 0 | 0 | #N/A |  | N/A | Funding not provided
81 | X5 | Niagara Peninsula Children's Centre School Authority | [12 empty] | Niagara Peninsula Children's Centre School Authority | 0 | 0 | N/A | 0 | 0 | #N/A |  | N/A | Funding not provided
82 | X6 | Ottawa Children's Treatment Centre School Authority/CHEO School | [12 empty] | Ottawa Children's Treatment Centre School Authority/CHEO School | 0 | 0 | N/A | 0 | 0 | #N/A |  | N/A | Funding not provided
83 | X7 | Consortium Center Jules-Léger | [12 empty] | Consortium Center Jules-Léger | 0 | 0 | N/A | 0 | 0 | #N/A |  | 5000 | Funding not provided